# InsureTech Platform

# Detailed Project Plan

Generated: 2025-12-16 19:20:24
Project Start: December 20, 2025
Planning Period: Dec 20, 2025 - Aug 1, 2026

# LabAid InsureTech Platform - Detailed Project Plan

## Version 1.1 December 16, 2025

________________________________________________________________________________

## Document Information

| Field | Value |
| --- | --- |
| **Project Name** | LabAid InsureTech Platform |
| **Document Type** | Detailed Project Plan |
| **Version** | 1.1 |
| **Date** | December 2024 (Planning Phase) |
| **Project Start** | December 20, 2025 |
| **Status** | Final - Aligned |
| **Owner** | Project Management Team |
| **Reviewers** | CEO, CTO, Business Admin, Technical Leads |

## Executive Summary

### Project Overview

The LabAid InsureTech Platform is a comprehensive digital insurance ecosystem designed to streamline insurance operations in Bangladesh. The platform enables:

End-to-end policy management

Digital claims processing

Multi-channel partner integration

Mobile-first customer experience

IoT-based usage-based insurance (UBI)

AI-powered automation and fraud detection

### Key Milestones

Project Start: December 20, 2025

M1 (March 1, 2026): Beta Launch - National Insurance Day Demo

M2 (April 14, 2026): Grand Launch - Pohela Boishakh Public Release

M3 (August 1, 2026): Complete Platform with IoT & AI Features

Note: Project spans December 2025 - August 2026 (8.5 months)

### Project Timeline

Timeline Overview: Complete sprint schedule from December 2025 to August 2026, showing 15 sprints across three major milestones.

### Capacity Utilization Over Time

Chart Description: Side-by-side comparison showing Available Capacity (green bars) vs Required Hours (blue bars) for each milestone phase. All phases show comfortable 68-73% utilization with adequate buffer.

### Project Capacity Summary (FINAL - REALISTIC CAPACITY - CORRECTED)

| Phase | Available Hours | Required Hours | Utilization | Status |
| --- | --- | --- | --- | --- |
| M1 (Beta) | 4,040 hrs | 2,740 hrs | 68% | ✅ **COMFORTABLE** |
| M2 (Launch) | 2,256 hrs | 1,641 hrs | 73% | ✅ **COMFORTABLE** |
| M3 (Complete) | 6,768 hrs | 4,863 hrs | 72% | ✅ Comfortable |
| **TOTAL** | **13,064 hrs** | **9,244 hrs** | **71%** | ✅ Achievable |

Capacity Adjustments Made:

M1: +48 hrs (Delowar calculation corrected from 173 to 221 hrs)

Total: +48 hrs (13,016 → 13,064 hrs)

### Critical Success Factors

✅ Existing Code Reuse: ~1,420 hours saved from proven services (Auth, Storage, Payment, IoT Broker)

✅ Mock-Based Parallel Development: All teams work simultaneously - Backend, Frontend, Mobile

✅ M1 Scope: Customer Mobile App (Android + iOS) + 2 web portals (Business Admin + Partner) with mocks (69% utilization)

✅ M2 Integration: Real API integration + Claims backend (73% utilization - comfortable)

✅ Team Allocation: CTO 50%, Mamoon 40%, Sagor 50%, Python 50%, Sujon 60%, Rumon 60%, React 70%, QA 60%, Mobile/Backend 90%

## Table of Contents

### 1. Team & Technology Stack

1.1 Team Structure & Roles

1.2 Technology Stack Overview

1.3 Architecture & Services

### 2. Project Timeline & Capacity

2.1 Available Working Hours by Phase

2.2 Capacity Summary Across All Phases

2.3 Utilization Notes

2.4 Holiday Impact Analysis

2.5 Critical Path Resources

### 3. Effort Estimation by Component

3.1 Estimation Methodology

3.2 M1 Services - Core Platform

3.2.1 User Service (Auth/AuthZ)

3.2.2 Policy Service

3.2.3 Claims Service (Moved to M2)

3.2.4 Payment Service

3.2.5 Document Service

3.2.6 Notification Service

3.2.7 Ticketing Service (Moved to M2)

3.2.8 Web Admin Portals

3.2.9 Mobile Apps (Moved to M2)

3.2.10 Infrastructure & DevOps

3.2.11 QA & Testing

3.2.12 UI/UX Design

3.3 M1 Summary - Total Effort

3.4 M2 Services - Desirable Features

3.5 M3 Services - Should Have & Future

3.6 Overall Project Summary

### 4. Sprint Planning & Timeline

4.1 Sprint Structure

4.2 Phase 1 Sprints (M1 Target: March 1, 2026)

Sprint 1: Dec 20 - Jan 2 (Foundation)

Sprint 2: Jan 3 - 16 (Policy Service Start)

Sprint 3: Jan 17 - 30 (Policy & Payment Complete)

Sprint 4: Jan 31 - Feb 13 (Integration)

Sprint 5: Feb 14 - 27 (Testing & Polish)

Sprint 5.5: Feb 28 - Mar 1 (Launch)

4.3 Phase 2 Sprints (M2 Target: April 14, 2026)

Sprint 6: Mar 2 - 15 (Claims & Mobile Start)

Sprint 7: Mar 16 - 29 (Mobile Development)

Sprint 8: Mar 30 - Apr 12 (Final Integration)

Buffer: Apr 13 - 14 (Grand Launch)

4.4 Phase 3 Sprints (M3 Target: August 1, 2026)

4.5 Sprint Capacity Planning

4.6 Sprint Velocity Tracking

4.7 Critical Path Analysis

4.8 Sprint Ceremonies Schedule

4.9 Sprint Success Criteria

### 5. RACI Matrix

5.1 Project Governance

5.2 Service Development RACI

5.3 Sprint Activities RACI

5.4 Deployment & Operations RACI

### 6. Resource Reassignment Strategy

File: 06_ResourceReassignment.md

6.1 Mobile Developer Reassignment (Week 8)

6.2 Cross-functional Support Strategy

6.3 Capacity Optimization

### 7. Risks & Mitigation

7.1 Technical Risks

7.2 Schedule Risks

7.3 Resource Risks

7.4 Business Risks

7.5 Mitigation Strategies

### 8. Requirements Distribution by Milestone

8.1 M1 Requirements (103 FRs)

8.2 M2 Requirements (92 FRs)

8.3 M3 Requirements (81 FRs)

8.4 Summary & Trade-offs

### 9. Person-Wise Responsibility

9.1 Individual Assignments

9.2 Accountability Matrix

9.3 Backup & Coverage

________________________________________________________________________________

## Document Change Log

| Version | Date | Changes | Author |
| --- | --- | --- | --- |
| 1.0 | Dec 16, 2025 | Initial aligned version - Fixed M1 effort estimation, aligned all planning docs | Farukhannan |
| 1.1 | Dec 2025 | Draft version with capacity issues ,grapgh, enhancement | AI Engine |

________________________________________________________________________________

## Approval Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | TBD |  |  |
| CTO | TBD |  |  |
| Business Admin | TBD |  |  |
| Project Manager | TBD |  |  |

## Team Members, Technology Stack & Existing Assets

### Team Member Details

#### Current Team (Available December 2025)

| # | Name | Role | Primary Tech Stack | Availability | Hours/Week | Responsibilities |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | **CTO** | Technical Lead & Gateway Dev | Go, Architecture | 50% coding, 50% management | 24 hrs | API Gateway, Kafka orchestration, IoT Broker, Storage Manager, Technical oversight |
| 2 | **Mamoon** | Senior Full Stack Developer | Node.js, React, MongoDB | 40% (other commitments) | 19 hrs | Payment Service completion, Ticketing Service, Full-stack features |
| 3 | **Sujon Ahmed** | Mid-level Full Stack Developer | Node.js, React, PostgreSQL | 100% (exhaust) | 48 hrs | Backend services, API development, Frontend support |
| 4 | **Rumon** | UI/UX Designer | Figma, Adobe XD, Design Systems | 100% (exhaust) | 48 hrs | Design system, Wireframes, Mockups, User experience |
| 5 | **Nur Hossain** | Android Developer | Kotlin, Java, Android SDK | 100% (exhaust) | 48 hrs | Android app development, Mobile API integration |
| 6 | **Sojol Ahmed** | iOS Developer | Swift, iOS SDK, Xcode | 100% (exhaust) | 48 hrs | iOS app development, Mobile API integration |
| 7 | **QA** | QA/Test Engineer | Selenium, Postman, Jest | 100% (exhaust) | 48 hrs | Manual & automated testing, Quality assurance |
| 8 | **Sagor** | DevOps Engineer | Docker, K8s, Go, Terraform | 50% (other projects) | 24 hrs | Infrastructure, CI/CD, Monitoring, Deployment |
| 9 | **React Dev** | Frontend Developer | React, Next.js, TypeScript | 100% (exhaust, joins Dec 18) | 48 hrs | Web portals, Admin panels, Frontend architecture |

December Team Capacity: ~7.4 FTE (355 hrs/week - CTO 50%, Mamoon 40%, Sagor 50%, others 100%)

________________________________________________________________________________

#### New Members Joining January 2026

| # | Name | Role | Primary Tech Stack | Join Date | Hours/Week | Responsibilities |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | **Project Manager** | Project Manager | Agile, Scrum, JIRA | Jan 1, 2026 | 48 hrs (exhaust) | Sprint planning, Team coordination, Stakeholder management |
| 11 | **Mr. Delowar** | **Senior C# Developer (Lead)** | C# .NET, gRPC, Microservices | Jan 15, 2026 | 48 hrs (exhaust) | Insurance Engine lead, Policy Service, Risk Management, Team mentoring |
| 12 | **C# Developer** | Mid-level C# Developer | C# .NET, gRPC, SQL Server | Jan 1, 2026 | 48 hrs (exhaust) | Partner/Agent Management, Analytics & Reporting services |
| 13 | **Python Dev 1** | Senior Python Developer | Python, FastAPI, gRPC | Jan 1, 2026 | 24 hrs (50% - M2/M3 focus) | AI Engine, LLM multi-agent network, AI assistant service |
| 14 | **Python Dev 2** | Python Developer | Python, FastAPI, gRPC | Jan 1, 2026 | 24 hrs (50% - M2/M3 focus) | MCP servers, AI integrations, Data processing |

Full Team Capacity (from Jan 15): ~11.4 FTE (547 hrs/week - Python devs 50% each, CTO 50%, Mamoon 40%, Sagor 50%, others 100%)

### Technology Stack by Service

#### Microservices Architecture

| Service | Language/Framework | Status | Developer(s) | Notes |
| --- | --- | --- | --- | --- |
| **API Gateway** | Go | 50% Ready (Existing) | CTO | Reuse + 50% new work |
| **Authentication** | Go | ✅ 100% Ready | CTO | Proven, tested code |
| **Authorization** | Go | ✅ 100% Ready | CTO | Proven, tested code |
| **DBManager** | Go | ✅ 100% Ready | CTO | Proven, tested code |
| **Storage Manager** | Go | ✅ 100% Ready | CTO | Proven, tested code |
| **IoT Broker** | Go | 80% Ready (Existing) | CTO | +20% for new requirements |
| **Payment Service** | Node.js | 70% Ready (Existing) | Mamoon | Bkash integration done |
| **Insurance Engine** | C# .NET + gRPC | 🆕 New | Mr. Delowar + C# Dev | Policy, Contract, Risk, Fraud |
| **Partner/Agent Mgmt** | C# .NET + gRPC | 🆕 New | C# Developer | Partner onboarding, verification |
| **AI Engine** | Python + gRPC | 🆕 New | Python Dev 1 & 2 | LLM, AI assistant, MCP servers |
| **Kafka Orchestration** | Go + Kafka | 🆕 New | CTO | Event streaming, Notification |
| **Ticketing Service** | Node.js | 🆕 New | Mamoon + Sujon | Customer support system |
| **Analytics & Reporting** | C# .NET + gRPC | 🆕 New | C# Developer | Business intelligence, Reports |

### Existing Assets & Reusable Code

#### CTO's Proven Go Services (Production-Ready)

| Service | Status | Lines of Code | Test Coverage | Description |
| --- | --- | --- | --- | --- |
| **Authentication Service** | ✅ 100% Ready | ~2,500 LOC | 90%+ | JWT-based auth, OAuth2, Session management |
| **Authorization Service** | ✅ 100% Ready | ~2,000 LOC | 85%+ | RBAC, Permission management, Policy engine |
| **DBManager Service** | ✅ 100% Ready | ~3,000 LOC | 85%+ | Database abstraction, Connection pooling, Query optimization |
| **Storage Manager** | ✅ 100% Ready | ~1,800 LOC | 80%+ | S3/Azure Blob integration, File management |
| **IoT Broker** | 80% Ready | ~4,000 LOC | 75%+ | MQTT broker, Device management, Data ingestion |
| **API Gateway** | 50% Ready | ~3,500 LOC | 70%+ | Routing, Rate limiting, API versioning |

Total Existing Code: ~16,800 LOC with high test coverage

Estimated Savings: ~1,200 development hours (equivalent to 6-8 weeks of work)

#### Mamoon's Payment Integration (70% Ready)

| Component | Status | Description |
| --- | --- | --- |
| **Bkash Integration** | ✅ Complete | Merchant account + Sandbox tested |
| **Payment Processing** | 70% Ready | Payment flow, Invoice generation |
| **Refund Logic** | 50% Ready | Partial refund handling |
| **Payment Gateway** | 70% Ready | Gateway abstraction, Multiple providers |

Estimated Savings: ~200 development hours

________________________________________________________________________________

### Development Tools & Infrastructure

#### Already Configured

| Category | Tool/Service | Status |
| --- | --- | --- |
| **Domain** | trendyco.insurance | ✅ Active |
| **Email** | Google Workspace | ✅ Configured |
| **Server** | Cloud Infrastructure | ✅ Setup |
| **Payment** | Bkash Merchant + Sandbox | ✅ Active |
| **Legal** | Trade License, BIN, TIN | ✅ Done |
| **Marketing** | Primary Website | ✅ Live |

#### Development Stack

| Category | Tools |
| --- | --- |
| **Backend Languages** | Go, C# .NET, Node.js, Python |
| **Frontend** | React, Next.js, TypeScript |
| **Mobile** | Kotlin (Android), Swift (iOS) |
| **Communication** | gRPC, REST API, WebSockets |
| **Message Queue** | Kafka, RabbitMQ |
| **Databases** | PostgreSQL, MongoDB, Redis |
| **Cloud** | AWS / Azure |
| **Containers** | Docker, Kubernetes |
| **CI/CD** | GitHub Actions, Jenkins |
| **Monitoring** | Prometheus, Grafana, Jaeger |
| **Testing** | Jest, Pytest, xUnit, Postman |

### Web Portals to Develop (React/Next.js)

ALIGNED M1 SCOPE: Only 2 portals for M1 to match capacity

| # | Portal Name | Primary Users | Priority | Notes |
| --- | --- | --- | --- | --- |
| 1 | **Business Admin Portal** | Business Managers | M1 | Product/policy management, core admin functions |
| 2 | **Partner Portal** | Insurance Partners | M1 | Partner dashboard, commission tracking |
| 3 | **System Admin Portal** | System Administrators | M2 | User management, system config |
| 4 | **Agent Portal** | Insurance Agents | M2 | Field agent operations |
| 5 | **Customer Support Portal** | Support Staff | M2 | Ticketing, customer queries |
| 6 | **Focal Person Portal** | Internal Coordinators | M3 | Partner management, approvals (per SRS M1, but deferred due to capacity) |
| 7 | **DevOps Portal** | DevOps Team (Prometheus, Grafana) | M3 | Infrastructure monitoring |
| 8 | **Database Manager Portal** | DBAs | M3 | Database administration |
| 9 | **Partner Admin Portal** | Partner Administrators | M3 | Advanced partner features |
| 10 | **General Staff Portal** | General Employees | M3 | Internal operations |
| 11 | **Vendor Portal** | Third-party Vendors | M3 | Vendor integrations |
| 12 | **Marketing Page Admin** | Marketing Team | M3 | Content management |

M1 Portals (with mock APIs): Business Admin + Partner ONLY (343 + 132 = 475 hrs)

M2 Portals: System Admin + Agent + Customer Support (3 portals)

M3 Portals: Remaining 7 portals

Note on Focal Person Portal: SRS marks FR-066 as M1 priority, but due to capacity constraints (M1 already at 69% utilization), deferred to M3. Manual focal person processes sufficient for M1 beta.

________________________________________________________________________________

### Mobile Applications

| App | Platform | Developer | Priority | Status |
| --- | --- | --- | --- | --- |
| **Customer App** | Android | Nur Hossain | M1 | With mock APIs, real integration M2 |
| **Customer App** | iOS | Sojol Ahmed | M1 | With mock APIs, real integration M2 |
| **Agent App** | Android | - | **NOT IN SCOPE** | Agents use web portal on tablets |
| **Agent App** | iOS | - | **NOT IN SCOPE** | Agents use web portal on tablets |

M1 Strategy: Customer App built in M1 with mock APIs (634 hrs). Real API integration in M2 (458 hrs).

Agent App Decision: NO agent mobile app per SRS requirements. Agents use Agent Portal (web) on tablets/desktops. Saves 580 hrs.

Reasoning: SRS does not specify agent mobile app as requirement. Web portal on tablet sufficient for field agents.

### Capacity Calculation

#### December 2025 (Pre-January Hires)

| Team Member | Availability | Hours/Week | Effective Hours |
| --- | --- | --- | --- |
| CTO | 50% | 24 hrs | 24 hrs |
| Mamoon | 40% | 19 hrs | 19 hrs |
| Sujon Ahmed | 100% (exhaust) | 48 hrs | 48 hrs |
| Rumon | 100% (exhaust) | 48 hrs | 48 hrs |
| Nur Hossain | 100% (exhaust) | 48 hrs | 48 hrs |
| Sojol Ahmed | 100% (exhaust) | 48 hrs | 48 hrs |
| QA | 100% (exhaust) | 48 hrs | 48 hrs |
| Sagor | 50% | 24 hrs | 24 hrs |
| React Dev (from Dec 18) | 100% (exhaust) | 48 hrs | 48 hrs |
| **Total December** | - | **355 hrs/week** | **355 hrs/week** |

December Sprint (2 weeks): 710 hours total capacity

________________________________________________________________________________

#### January 2026+ (Full Team)

| Team Member | Availability | Hours/Week | Effective Hours |
| --- | --- | --- | --- |
| Existing Team (9) | Mixed | 355 hrs | 355 hrs |
| Project Manager | 100% (exhaust) | 48 hrs | 48 hrs |
| Mr. Delowar (from Jan 15) | 100% (exhaust) | 48 hrs | 48 hrs (prorated) |
| C# Developer | 100% (exhaust) | 48 hrs | 48 hrs |
| Python Dev 1 | 50% | 24 hrs | 24 hrs |
| Python Dev 2 | 50% | 24 hrs | 24 hrs |
| **Total January+** | - | **547 hrs/week** | **547 hrs/week** |

January Sprint (2 weeks): 1,094 hours total capacity

With Mr. Delowar joining mid-month (Jan 15): His hours prorated for first sprint

### Buffer Strategy: 10%

Rationale for 10% Buffer:

Existing code reuse reduces unknowns

Proven, tested components (Auth, DBManager, etc.)

Experienced team members (CTO, Mamoon)

Clear architecture already established

Buffer Allocation:

Bug fixes & rework: 4%

Integration issues: 3%

Meetings & reviews: 2%

Unexpected blockers: 1%

Total Buffer: 10% of estimated effort

________________________________________________________________________________

### Risk Mitigation Through Existing Assets

| Risk | Mitigation via Existing Assets |
| --- | --- |
| Authentication delays | ✅ 100% ready Go service (CTO) |
| Authorization complexity | ✅ 100% ready Go service (CTO) |
| Database performance | ✅ Proven DBManager service |
| Storage issues | ✅ Storage Manager ready |
| Payment integration | ✅ Bkash integration 70% done (Mamoon) |
| IoT requirements | ✅ IoT Broker 80% ready |
| API Gateway setup | ✅ 50% ready, proven architecture |

Estimated Risk Reduction: 40-50% due to existing proven components

# Working Days Chart & Calendar Analysis

## Project Timeline Overview

### Milestone Dates

M1 - Beta Launch: March 1, 2026 (National Insurance Day)

M2 - Grand Launch: April 14, 2026 (Pohela Boishakh)

M3 - Complete Platform: August 1, 2026

______________________________________________________________________________

## Working Days Calculation

### M1 Period: December 20, 2025 - March 1, 2026

Calendar Breakdown:

Start Date: December 20, 2025

End Date: March 1, 2026

Total Calendar Days: 72 days

Holidays in M1 Period:

| Date | Day | Holiday Name | Status |
| --- | --- | --- | --- |
| Dec 25, 2025 | Thursday | Christmas Day | Confirmed |
| Feb 4, 2026 | Wednesday | Shab-e-Barat | Moon Dependent |
| Feb 21, 2026 | Saturday | Intl. Mother Language Day | Confirmed |

Total Holidays: 3 days

Weekends in M1 Period:

Working Days: Saturday to Thursday (6 days/week)

Friday is weekend

Approximate Fridays: ~10 days

Working Days Calculation:

Calendar Days:        72 days
Minus Holidays:       -3 days
Minus Weekends:       -10 days
= Net Working Days:   59 days

Effective Working Days for M1: 59 days

### M2 Period: March 2, 2026 - April 14, 2026

Calendar Breakdown:

Start Date: March 2, 2026 (Day after M1 launch)

End Date: April 14, 2026 (M2 Launch Day)

Total Calendar Days: 44 days

Holidays in M2 Period:

| Date | Day | Holiday Name | Status |
| --- | --- | --- | --- |
| Mar 18, 2026 | Wednesday | Shab-e-Qadr | Moon Dependent |
| Mar 20, 2026 | Friday | Jumatul Bidah | Moon Dependent |
| Mar 21, 2026 | Saturday | Eid-ul-Fitr Day 1 | Moon Dependent |
| Mar 22, 2026 | Sunday | Eid-ul-Fitr Day 2 | Moon Dependent |
| Mar 23, 2026 | Monday | Eid-ul-Fitr Day 3 | Moon Dependent |
| Mar 24, 2026 | Tuesday | Eid-ul-Fitr Day 4 (Extended) | Moon Dependent |
| Mar 25, 2026 | Wednesday | Eid-ul-Fitr Day 5 (Extended) | Moon Dependent |
| Mar 26, 2026 | Thursday | Independence Day | Confirmed |
| Apr 14, 2026 | Tuesday | Pohela Boishakh (Launch Day) | Confirmed |

Total Holidays: 9 days (including launch day)

Weekends in M2 Period:

Working Days: Saturday to Thursday (6 days/week)

Friday is weekend

Approximate Fridays: ~6 days

Working Days Calculation:

Calendar Days:        44 days
Minus Holidays:       -9 days
Minus Weekends:       -6 days
= Net Working Days:   29 days

Effective Working Days for M2: 29 days

### M3 Period: April 15, 2026 - August 1, 2026

Calendar Breakdown:

Start Date: April 15, 2026 (Day after M2 launch)

End Date: August 1, 2026

Total Calendar Days: 109 days

Holidays in M3 Period:

| Date | Day | Holiday Name | Status |
| --- | --- | --- | --- |
| May 1, 2026 | Friday | May Day | Confirmed |
| May 27, 2026 | Wednesday | Eid-ul-Adha Day 1 | Moon Dependent |
| May 28, 2026 | Thursday | Eid-ul-Adha Day 2 | Moon Dependent |
| May 29, 2026 | Friday | Eid-ul-Adha Day 3 | Moon Dependent |
| May 30, 2026 | Saturday | Eid-ul-Adha Day 4 (Extended) | Moon Dependent |
| Aug 15, 2026 | Saturday | National Mourning Day | Confirmed |

Total Holidays: 5 days (May 1 is Friday, already weekend)

Weekends in M3 Period:

Working Days: Saturday to Thursday (6 days/week)

Friday is weekend

Approximate Fridays: ~15 days

Working Days Calculation:

Calendar Days:        109 days
Minus Holidays:       -5 days
Minus Weekends:       -15 days
= Net Working Days:   89 days

Effective Working Days for M3: 89 days

## Summary: Total Working Days

| Phase | Period | Calendar Days | Holidays | Weekends | Working Days |
| --- | --- | --- | --- | --- | --- |
| **M1** | Dec 20, 2025 - Mar 1, 2026 | 72 | 3 | 10 | **59 days** |
| **M2** | Mar 2, 2026 - Apr 14, 2026 | 44 | 9 | 6 | **29 days** |
| **M3** | Apr 15, 2026 - Aug 1, 2026 | 109 | 5 | 15 | **89 days** |
| **TOTAL** | Dec 20, 2025 - Aug 1, 2026 | 225 | 17 | 31 | **177 days** |

## Work Hours Calculation

Assumptions:

Work Week: Saturday to Thursday (6 days/week)

Work Hours per Day: 8 hours

Work Hours per Week: 48 hours (6 days × 8 hours)

### Team Size by Phase

M1 Phase:

December 2025: 9 members available

January 2026 onwards: 14 members available

M2 & M3 Phase:

Full team: 14 members available

### Available Team Hours (Before Buffer)

M1 Calculation:

December portion: ~2 weeks × 9 members × 48 hrs/week = 864 hours

January-March portion: ~8 weeks × 14 members × 48 hrs/week = 5,376 hours

Total M1 (Gross): 6,240 hours

M2 Calculation:

29 working days = ~5.8 weeks

14 members × 48 hrs/week × 5.8 weeks = 3,916 hours

Total M2 (Gross): 3,916 hours

M3 Calculation:

89 working days = ~17.8 weeks

14 members × 48 hrs/week × 17.8 weeks = 11,980 hours

Total M3 (Gross): 11,980 hours

________________________________________________________________________________

## Buffer Strategy: 10% Strict Reserve

Buffer Policy:

Reserve 10% of all available hours for:

Unexpected bugs and rework

Production incidents

Emergency changes

Technical debt

Testing extensions

### Net Available Hours (After 10% Buffer)

| Phase | Gross Hours | 10% Buffer | Net Available Hours |
| --- | --- | --- | --- |
| **M1** | 6,240 hrs | 624 hrs | **5,616 hrs** |
| **M2** | 3,916 hrs | 392 hrs | **3,524 hrs** |
| **M3** | 11,980 hrs | 1,198 hrs | **10,782 hrs** |
| **TOTAL** | 22,136 hrs | 2,214 hrs | **19,922 hrs** |

________________________________________________________________________________

## Critical Notes

M1 is the most critical phase with foundational services and infrastructure

M2 has limited time due to heavy Eid holidays (5 days) + Independence Day + Launch Day

M3 has comfortable time for desirable features and enhancements

Buffer is non-negotiable - must maintain 10% reserve for each phase

Moon-dependent holidays may shift by 1-2 days; plan conservatively

Launch days (M1, M2) are counted as holidays since full development work is not feasible

## 2. Team Capacity Analysis

### 2.1 Available Working Hours by Phase

#### Phase 1: Dec 20, 2025 - March 1, 2026 (M1)

Calendar Days: 72 days

Holidays: 2 days (Dec 25, 2025 Christmas, Feb 21, 2026 Language Day)

Weekends: ~20 days (Fridays + Saturdays)

Total Working Days: 50 days

Total Weeks: 10 weeks

December Team (Dec 20-31): 9 members - 2 weeks

January+ Team (Jan 1-Mar 1): 14 members - 8 weeks

| Role/Member | Availability | Dec Hours (2 wks) | Jan+ Hours (8 wks) | Total M1 Hours |
| --- | --- | --- | --- | --- |
| **CTO** | 50% (50% other projects) | 48 hrs | 192 hrs | 240 hrs |
| **Mamoon** | 40% (other commitments) | 38 hrs | 154 hrs | 192 hrs |
| **Sujon Ahmed** | 60% (realistic) | 58 hrs | 230 hrs | 288 hrs |
| **Rumon (UI/UX)** | 60% (realistic) | 58 hrs | 230 hrs | 288 hrs |
| **Nur Hossain (Android)** | 90% (realistic) | 86 hrs | 346 hrs | 432 hrs |
| **Sojol Ahmed (iOS)** | 90% (realistic) | 86 hrs | 346 hrs | 432 hrs |
| **QA** | 60% (realistic testing) | 58 hrs | 230 hrs | 288 hrs |
| **Sagor (DevOps)** | 50% (other projects) | 48 hrs | 192 hrs | 240 hrs |
| **React Dev** | 70% (realistic) | 67 hrs | 269 hrs | 336 hrs |
| **Project Manager** | 90% (from Jan 1) | 0 hrs | 346 hrs | 346 hrs |
| **Mr. Delowar** | 90% (from Jan 15) | 0 hrs | 221 hrs | 221 hrs |
| **C# Developer** | 90% (realistic) | 0 hrs | 346 hrs | 346 hrs |
| **Python Dev 1** | 50% (M2/M3 focus) | 0 hrs | 192 hrs | 192 hrs |
| **Python Dev 2** | 50% (M2/M3 focus) | 0 hrs | 192 hrs | 192 hrs |
| **TOTAL M1** | - | **604 hrs** | **3,436 hrs** | **4,040 hrs** |

Note on Mr. Delowar: Joins Jan 15, 2026 (mid-M1). Calculation: Jan 15 to Mar 1 = 31 working days × 8 hrs/day × 90% = 223 hrs (adjusted to 221 hrs after weekend/holiday exclusion).

#### Phase 2: March 2 - April 14, 2026 (M1 to M2)

Calendar Days: 44 days (M1 launch on March 1, M2 starts March 2)

Holidays: 7 days (Eid-ul-Fitr Mar 31-Apr 2 = 3 days, Independence Day Mar 26, Pohela Boishakh Apr 14 = launch day)

Weekends: ~12 days

Total Working Days: 25 days

Total Weeks: 5 weeks

Full Team Available: 14 members

| Role/Member | Availability | M2 Hours (5 wks) |
| --- | --- | --- |
| **CTO** | 50% (50% other projects) | 120 hrs |
| **Mamoon** | 40% (other commitments) | 96 hrs |
| **Sujon Ahmed** | 60% (realistic) | 144 hrs |
| **Rumon (UI/UX)** | 60% (realistic) | 144 hrs |
| **Nur Hossain (Android)** | 90% (realistic) | 216 hrs |
| **Sojol Ahmed (iOS)** | 90% (realistic) | 216 hrs |
| **QA** | 60% (realistic testing) | 144 hrs |
| **Sagor (DevOps)** | 50% (other projects) | 120 hrs |
| **React Dev** | 70% (realistic) | 168 hrs |
| **Project Manager** | 90% (oversight) | 216 hrs |
| **Mr. Delowar** | 90% (realistic) | 216 hrs |
| **C# Developer** | 90% (realistic) | 216 hrs |
| **Python Dev 1** | 50% (M3 focus) | 120 hrs |
| **Python Dev 2** | 50% (M3 focus) | 120 hrs |
| **TOTAL M2** | - | **2,256 hrs** |

#### Phase 3: April 15 - August 1, 2026 (M2 to M3)

Calendar Days: 109 days

Holidays: 3 days (May 1 Labor Day, May 23 Buddha Purnima, Aug 15 National Mourning Day)

Weekends: ~30 days

Total Working Days: 76 days

Total Weeks: 15.2 weeks (~15 weeks)

Full Team Available: 14 members

| Role/Member | Availability | M3 Hours (15 wks) |
| --- | --- | --- |
| **CTO** | 50% (50% other projects) | 360 hrs |
| **Mamoon** | 40% (other commitments) | 288 hrs |
| **Sujon Ahmed** | 60% (realistic) | 432 hrs |
| **Rumon (UI/UX)** | 60% (realistic) | 432 hrs |
| **Nur Hossain (Android)** | 90% (realistic) | 648 hrs |
| **Sojol Ahmed (iOS)** | 90% (realistic) | 648 hrs |
| **QA** | 60% (realistic testing) | 432 hrs |
| **Sagor (DevOps)** | 50% (other projects) | 360 hrs |
| **React Dev** | 70% (realistic) | 504 hrs |
| **Project Manager** | 90% (oversight) | 648 hrs |
| **Mr. Delowar** | 90% (realistic) | 648 hrs |
| **C# Developer** | 90% (realistic) | 648 hrs |
| **Python Dev 1** | 50% (M3 AI focus) | 360 hrs |
| **Python Dev 2** | 50% (M3 AI focus) | 360 hrs |
| **TOTAL M3** | - | **6,768 hrs** |

### 2.2 Capacity Summary Across All Phases

| Phase | Duration | Total Available | Notes |
| --- | --- | --- | --- |
| Phase 1 (to M1) | 50 days | 4,040 hrs | CTO 50%, Mamoon 40%, Sagor 50%, Python 50%, Sujon 60%, Rumon 60%, React 70%, QA 60%, Delowar 90% (from Jan 15) |
| Phase 2 (M1-M2) | 25 days | 2,256 hrs | Same distribution as M1 |
| Phase 3 (M2-M3) | 76 days | 6,768 hrs | Same distribution, Python devs 50% for AI work |
| **TOTAL** | **151 days** | **13,064 hrs** | All phases with realistic capacity (M1 adjusted +48 hrs for Delowar correction, -1 day for Feb 21 holiday) |

Key Capacity Notes:

CTO: 50% coding time (50% management + other projects)

Mamoon: 40% time (other commitments)

Sagor (DevOps): 50% time (other projects)

Python Devs: 50% time each (focus on M2/M3 AI features)

Sujon Ahmed: 60% time (realistic with other tasks)

Rumon (UI/UX): 60% time (design-heavy periods)

React Dev: 70% time (realistic with blockers)

QA: 60% time (realistic testing utilization)

Project Manager: 90% time (joins Jan 1)

Mobile Devs (Nur, Sojol): 90% realistic utilization

Backend Devs (Delowar, C# Dev): 90% realistic utilization

Mr. Delowar: Joins Jan 15, 2026 (mid-sprint) at 90%

### 2.3 Utilization Notes

Utilization Targets Explained:

Backend (85%): High utilization due to core service development

Frontend (85%): High utilization for web admin panel

Mobile (85%): High utilization initially, then available for reassignment

DevOps (75%): Infrastructure setup, CI/CD, ongoing support

QA (80%): Testing, automation, continuous quality assurance

UI/UX (70%): Design system, prototypes, handoff to developers

Buffer Time Allocation (18.5% overall):

Meetings, communication, code reviews: 5%

Bug fixes and rework: 6%

Learning and research: 3%

Unexpected issues and blockers: 4.5%

### 2.4 Holiday Impact Analysis

M1 Period (Dec 20, 2025 - Mar 1, 2026) Holidays:

| Holiday | Date | Impact | Notes |
| --- | --- | --- | --- |
| Christmas Day | Dec 25, 2025 | 1 day loss | Already excluded from working days |
| Intl. Mother Language Day | Feb 21, 2026 | 1 day loss | National holiday in Bangladesh |
| **M1 Total** | - | **2 days** | Both holidays excluded from working day calculation |

M2 Period (Mar 2 - Apr 14, 2026) Holidays:

| Holiday | Date | Impact | Notes |
| --- | --- | --- | --- |
| Eid-ul-Fitr | Mar 31 - Apr 2, 2026 | 3 days loss | Eid break |
| Independence Day | Mar 26, 2026 | 1 day loss | Already excluded from working days |
| Pohela Boishakh (M2 Launch) | Apr 14, 2026 | 1 day loss | Launch day - limited dev work |
| **M2 Total** | - | **5 days** | Included in M2 calculation (7 with weekends) |

M3 Period (Apr 15 - Aug 1, 2026) Holidays:

| Holiday | Date | Impact | Notes |
| --- | --- | --- | --- |
| May Day | May 1, 2026 | 1 day loss | Labor Day |
| Buddha Purnima | May 23, 2026 | 1 day loss | Already excluded from working days |
| National Mourning Day | Aug 15, 2026 | 1 day loss | Falls after M3 deadline |
| **M3 Total** | - | **2-3 days** | Included in M3 calculation |

Overall Holiday Impact:

| Phase | Holidays | Team-Hours Lost | Mitigation |
| --- | --- | --- | --- |
| M1 | 2 days | ~96 team-hours | Both holidays (Dec 25 + Feb 21) excluded from capacity calculation |
| M2 | 5 days | ~240 team-hours | Already excluded from capacity calculation |
| M3 | 3 days | ~144 team-hours | Already excluded from capacity calculation |
| **Total** | **10 days** | **~480 team-hours** | All holidays accounted for in working day calculations |

### 2.5 Critical Path Resources

Backend Developers (Highest Demand):

Required for all core services

Critical path for M1 delivery

Proposed mitigation: Mobile developers assist with API testing and documentation

Frontend Developer (Single Point of Failure):

Only one resource for entire web admin panel

Risk: Bottleneck for M1 delivery

Proposed mitigation: Mobile developers assist with component development after mobile MVP

Mobile Developers (Early Finish Opportunity):

Mobile apps have lower complexity than web panel

Expected to finish 2-3 weeks before M1

Reassignment Strategy: Support backend API testing, frontend component development, documentation

## 3. Effort Estimation by Service/Component

### 3.1 Estimation Methodology

Unit: Story Points converted to hours (1 SP = 6-8 hours)

Complexity Factors: Technical complexity, dependencies, team experience

Estimation Approach: Three-point estimation (Optimistic, Most Likely, Pessimistic)

Buffer: 10% added for unknowns and integration testing (reduced from 20% due to existing proven code)

### 3.1.1 Existing Code Reuse Impact

Proven Components (No Development Needed):

✅ Authentication Service (Go) - Saves ~250 hours

✅ Authorization Service (Go) - Saves ~220 hours

✅ DBManager Service (Go) - Saves ~280 hours

✅ Storage Manager Service (Go) - Saves ~180 hours

✅ IoT Broker (Go) - 80% ready, Saves ~200 hours

✅ API Gateway (Go) - 50% ready, Saves ~150 hours

✅ Payment Service (Node.js) - 70% ready, Saves ~140 hours

Total Savings from Existing Code: ~1,420 hours

Reduced Buffer Justification: Existing tested code = lower risk = 10% buffer instead of 20%

________________________________________________________________________________

### 3.2 M1 Services - Core Platform (Must Have for Soft Launch - March 1st)

M1 SCOPE: Minimal viable features for beta testing and demo on National Insurance Day

Focus: User registration, basic policy purchase flow, partner portal foundation

NOT INCLUDED IN M1: Claims processing (M2), Mobile apps (M2), Advanced features

#### 3.2.1 User Service (Authentication & Authorization)

Priority: M1 | Owner: CTO (Go Services - Existing Code 100% Ready)

| Feature | Complexity | Estimated Hours | Status |
| --- | --- | --- | --- |
| Authentication (Login/Logout/JWT) | Medium | ✅ 0 hrs | **100% Ready** |
| Authorization (RBAC) | High | ✅ 0 hrs | **100% Ready** |
| User Registration (Phone OTP) | Medium | ✅ 0 hrs | **100% Ready** |
| Profile Management (CRUD) | Low | ✅ 0 hrs | **100% Ready** |
| Password Reset & Recovery | Medium | ✅ 0 hrs | **100% Ready** |
| Session Management | Medium | ✅ 0 hrs | **100% Ready** |
| Multi-factor Authentication | High | ✅ 0 hrs | **100% Ready** |
| Insurance-specific User Roles (8 roles) | Low | 16 hrs | Role config only |
| API Documentation Update | Low | 8 hrs | Update for insurance domain |
| Integration Tests (Insurance context) | - | 16 hrs | Context-specific testing |
| **SUBTOTAL** | - | **40 hrs** | - |
| **Buffer (10%)** | - | **4 hrs** | - |
| **TOTAL** | - | **44 hrs** | - |

Team Assignment: CTO (40% time - 19 hrs/week) - Can complete in 3 days

Savings: ~400 hours from proven authentication/authorization system

#### 3.2.2 Insurance Engine - Policy Service (M1 - Core Only)

Priority: M1 | Owner: Mr. Delowar (C# .NET Lead) + C# Mid-level Developer

M1 Scope: Basic policy creation and management only. Advanced features moved to M2.

| Feature | Complexity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- | --- |
| Insurance Domain Models (C#) | High | 48 hrs | DBManager (existing) | M1 |
| Policy CRUD Operations (gRPC) | Medium | 40 hrs | User Service (existing) | M1 |
| Basic Policy Search & Filters | Low | 24 hrs | Policy CRUD | M1 |
| Premium Calculation Engine (Simple) | High | 56 hrs | Actuarial formulas | M1 |
| Beneficiary Management | Medium | 24 hrs | Policy CRUD | M1 |
| Policy Status Management | Low | 16 hrs | Policy CRUD | M1 |
| gRPC API Design & Implementation | Medium | 32 hrs | Core features | M1 |
| Unit & Integration Tests (.NET) | - | 48 hrs | Core features | M1 |
| **SUBTOTAL** | - | **288 hrs** | - | - |
| **Buffer (10%)** | - | **29 hrs** | - | - |
| **TOTAL M1** | - | **317 hrs** | - | - |

Moved to M2 (460 hrs): Policy Renewal Logic, Cancellation, History/Versioning, Contract Management, Coverage/Riders, Risk Assessment

Team Assignment: Mr. Delowar (Jan 15+) + C# Mid Dev (Jan 1+)

2 devs × 96 hrs/week = can complete in 3.5 weeks

Note: Heavy use of existing DBManager (saves 280 hrs) and Auth services (saves 250 hrs)

#### 3.2.3 Claim Service

Priority: M2 (NOT M1!) | Owner: Backend Team (Delowar + C# Dev)

⚠️ CONFIRMED M2 PRIORITY - Claims moved to M2 after Grand Launch

SRS Analysis: FR-041 to FR-058 show mixed M1/M2/M3 priorities

Decision: Move ALL claims to M2 for capacity management

M1 focus: Policy purchase flow for beta demo only

Claims processing starts after Grand Launch (April 14, 2026)

Reasoning: M1 already at 69% capacity with core features

| Feature | Complexity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- | --- |
| Claim Models & Schema | Medium | 24 hrs | Policy Service | M2 |
| Claim Filing & Submission | Medium | 48 hrs | Policy, Document | M2 |
| Claim Status Tracking | Low | 24 hrs | Claim Filing | M3 |
| Claim Approval Workflow | High | 72 hrs | User Service | M3 |
| Claim Assessment Logic | High | 64 hrs | Policy Service | M3 |
| Claim Settlement | High | 56 hrs | Payment Service | M3 |
| Fraud Detection (Basic) | High | 64 hrs | Claim Models | M3 |
| Claim Document Management | Medium | 40 hrs | Document Service | M2 |
| Claim History & Reporting | Medium | 32 hrs | Claim Models | M3 |
| Claim Notifications | Low | 24 hrs | Notification Service | M2 |
| API Documentation | Low | 16 hrs | All features | M2 |
| Unit & Integration Tests | - | 64 hrs | All features | M2 |
| **SUBTOTAL** | - | **528 hrs** | - | - |
| **Buffer (20%)** | - | **106 hrs** | - | - |
| **TOTAL M2** | - | **634 hrs** | - | - |

Team Assignment: 3 Backend Devs in M2 phase (after March 1st)

#### 3.2.4 Payment Service

Priority: M1 | Owner: Mamoon (Node.js - 70% Existing Code)

| Feature | Complexity | Estimated Hours | Status | Priority |
| --- | --- | --- | --- | --- |
| Payment Gateway Integration (Bkash) | High | ✅ 0 hrs | **100% Ready** | M1 |
| Payment Processing (Premium) | High | 16 hrs | Minor adaptation | M1 |
| Invoice Generation | Medium | 8 hrs | 70% ready, polish | M1 |
| Receipt Generation | Low | 12 hrs | Customization | M1 |
| Payment History & Tracking | Medium | 8 hrs | 70% ready, adapt | M1 |
| Payment Notifications | Low | 8 hrs | Integration | M1 |
| Failed Payment Handling | Medium | 12 hrs | Enhancement | M1 |
| API Documentation Update | Low | 8 hrs | Update docs | M1 |
| Unit & Integration Tests | - | 24 hrs | Additional tests | M1 |
| **SUBTOTAL M1** | - | **96 hrs** | - | - |
| **Buffer (10%)** | - | **10 hrs** | - | - |
| **TOTAL M1** | - | **106 hrs** | - | - |

Moved to M2 (171 hrs):

Payment Processing (Claims) - 32 hrs (Claims are M2)

Refund Processing - 24 hrs (Policy cancellation is M2)

Payment Reconciliation - 40 hrs (Advanced feature)

Multi-gateway Support (Nagad/Cards) - 48 hrs (Nice to have)

Buffer - 27 hrs

Team Assignment: Mamoon (50% time = 24 hrs/week) - Can complete in ~4.5 weeks

Savings: ~450 hours from existing Bkash integration and payment infrastructure

#### 3.2.5 Document Service (Storage Manager)

Priority: M1 | Owner: CTO (Go - Existing Code 100% Ready) + Sagor

| Feature | Complexity | Estimated Hours | Status | Priority |
| --- | --- | --- | --- | --- |
| File Upload (Multi-format) | Medium | ✅ 0 hrs | **100% Ready** | M1 |
| Cloud Storage Integration (S3/Azure) | High | ✅ 0 hrs | **100% Ready** | M1 |
| Document Metadata Management | Medium | ✅ 0 hrs | **100% Ready** | M1 |
| Document Retrieval & Download | Low | ✅ 0 hrs | **100% Ready** | M1 |
| Document Versioning | Medium | ✅ 0 hrs | **100% Ready** | M1 |
| Document Security & Access Control | High | 8 hrs | Integration with Auth | M1 |
| Insurance Document Types | Low | 12 hrs | Policy, KYC docs config | M1 |
| Document Tagging & Categorization | Low | 16 hrs | Basic categories | M1 |
| API Documentation Update | Low | 8 hrs | Update for insurance | M1 |
| Unit & Integration Tests | - | 16 hrs | Additional tests | M1 |
| **SUBTOTAL M1** | - | **60 hrs** | - | - |
| **Buffer (10%)** | - | **6 hrs** | - | - |
| **TOTAL M1** | - | **66 hrs** | - | - |

Moved to M2/M3 (119 hrs):

Document Preview Generation - 32 hrs (Nice to have)

OCR Integration (Basic) - 48 hrs (Advanced feature for claims)

Advanced tagging - 8 hrs

Buffer - 11 hrs

Team Assignment: CTO (40% time = 19 hrs/week) + Sagor - Can complete in ~2 weeks

Savings: ~450 hours from existing Storage Manager service (S3, versioning, security all ready)

#### 3.2.6 Notification Service (Kafka Orchestration)

Priority: M1 (Basic) | Owner: CTO (Go + Kafka - 80% Ready from IoT Broker)

| Feature | Complexity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- | --- |
| Kafka Setup & Configuration | Medium | 24 hrs | IoT Broker (80% ready) | M1 |
| Email Integration (SMTP/SendGrid) | Medium | 24 hrs | Kafka | M1 |
| SMS Integration (Local provider) | Medium | 24 hrs | Kafka | M1 |
| Basic Template System | Low | 24 hrs | Email/SMS | M1 |
| Notification Queue | Medium | 16 hrs | Kafka (reuse broker) | M1 |
| Policy Purchase Event Triggers | Low | 16 hrs | Policy service | M1 |
| API Documentation | Low | 8 hrs | Core features | M1 |
| Unit & Integration Tests | - | 24 hrs | Core features | M1 |
| **SUBTOTAL M1** | - | **160 hrs** | - | - |
| **Buffer (10%)** | - | **16 hrs** | - | - |
| **TOTAL M1** | - | **176 hrs** | - | - |

Moved to M2 (255 hrs):

Push Notification (FCM) - 40 hrs (Mobile apps are M2)

Advanced Template Management - 16 hrs

Notification Preferences - 24 hrs

Notification History & Tracking - 24 hrs

Multi-language Support - 32 hrs (Bengali for M2)

Advanced Event Triggers (Claims, Renewals) - 32 hrs

Additional docs & tests - 64 hrs

Buffer - 23 hrs

Team Assignment: CTO (40% time = 19 hrs/week) - Can complete in ~9 weeks alongside other tasks

Savings: ~200 hours from existing IoT Broker/Kafka infrastructure

#### 3.2.7 Ticketing/Customer Service

Priority: M2 (NOT M1!) | Owner: Mamoon + Sujon Ahmed (Node.js)

⚠️ MOVED TO M2 - Customer support tickets not critical for beta demo

M1 focus: Policy purchase flow demonstration

Support can be handled manually via phone/email in beta

Full ticketing system after Grand Launch (April 14)

| Feature | Complexity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- | --- |
| Ticket Management System | Medium | 48 hrs | User Service (existing) | M2 |
| Ticket Status Workflow | Medium | 32 hrs | Ticket CRUD | M2 |
| Customer Communication | Medium | 32 hrs | Notification Service | M2 |
| FAQ Management (Bengali/English) | Medium | 32 hrs | CMS-style | M2 |
| Knowledge Base | Low | 24 hrs | Document linking | M2 |
| Support Agent Assignment | Medium | 32 hrs | User Service (existing) | M2 |
| Ticket Priority & Escalation | Medium | 32 hrs | Workflow | M3 |
| SLA Tracking | Medium | 24 hrs | Time-based rules | M3 |
| Insurance Query Templates | Low | 16 hrs | Common queries | M2 |
| API Documentation | Low | 16 hrs | All features | M2 |
| Unit & Integration Tests | - | 32 hrs | All features | M2 |
| **SUBTOTAL** | - | **320 hrs** | - | - |
| **Buffer (10%)** | - | **32 hrs** | - | - |
| **TOTAL M2** | - | **352 hrs** | - | - |

Team Assignment: Mamoon + Sujon Ahmed in M2 phase (March-April)

Note: Basic contact form sufficient for M1 beta

#### 3.2.8 Web Admin Portals (Multiple Portals - React/Next.js)

Priority: M1 (2 Portals), M2 (1 Portal) | Owner: React Dev (starts Dec 18)

REVISED SCOPE: Minimal portals per phase

M1 (March 1): Business Admin + Shared Infrastructure only

M2 (April 14): Partner Portal

M3 (June+): All other 10 portals

| Portal/Feature | Complexity | Estimated Hours | Priority | Notes |
| --- | --- | --- | --- | --- |
| **M1 - Shared Components & Infrastructure** |  |  |  |  |
| Design System Setup (Tailwind/Shadcn) | Medium | 40 hrs | M1 | Reusable foundation |
| Authentication UI (Shared) | Low | 24 hrs | M1 | One time setup |
| Navigation & Layout System | Medium | 32 hrs | M1 | Reusable template |
| State Management (Redux/Zustand) | Medium | 24 hrs | M1 | Simplified |
| API Integration Layer | Medium | 32 hrs | M1 | Core only |
| **Business Admin Portal** | High | 72 hrs | M1 | Product/Policy mgmt CRUD |
| Notification Center (Basic) | Low | 16 hrs | M1 | Simple alerts |
| Responsive Design | Medium | 24 hrs | M1 | Mobile friendly |
| Error Handling & Validation | Low | 16 hrs | M1 | Core features |
| Testing (Unit + E2E) | - | 32 hrs | M1 | Critical paths |
| **SUBTOTAL M1** | - | **312 hrs** | - | - |
| **Buffer (10%)** | - | **31 hrs** | - | - |
| **TOTAL M1** | - | **343 hrs** | - | - |
| **M2 - Partner Portal** |  |  |  |  |
| Partner Portal Dashboard | Medium | 48 hrs | M2 | View policies/commissions |
| Partner Profile Management | Low | 24 hrs | M2 | KYB info |
| Performance Analytics (Basic) | Medium | 32 hrs | M2 | Charts/reports |
| Testing | - | 16 hrs | M2 | Integration tests |
| **SUBTOTAL M2** | - | **120 hrs** | - | - |
| **Buffer (10%)** | - | **12 hrs** | - | - |
| **TOTAL M2** | - | **132 hrs** | - | - |

Moved to M3 (10 portals = ~800 hrs):

System Admin Portal - 48 hrs

Agent Portal - 80 hrs

Customer Support Portal - 72 hrs

DevOps Portal - 64 hrs

Database Manager Portal - 64 hrs

Focal Person Portal - 80 hrs

Partner Admin Portal - 72 hrs

General Staff Portal - 64 hrs

Vendor Portal - 64 hrs

Marketing Admin Portal - 56 hrs

Advanced features - 136 hrs

Team Assignment:

React Dev (Dec 18-Mar 1): M1 portals = 343 hrs ÷ 48 hrs/week = 7.2 weeks ✓ Achievable

React Dev (Mar 1-Apr 14): M2 Partner Portal = 132 hrs easily fits in 6 weeks

#### 3.2.9 Mobile Apps (Android & iOS - Native)

Priority: M1 (WITH MOCK SERVERS) | Owner: Nur Hossain (Android) + Sojol Ahmed (iOS)

✅ M1 STRATEGY - PARALLEL DEVELOPMENT:

Backend team provides mock server (Sujon Ahmed - 40 hrs)

Mobile apps develop against mock APIs in M1 (Customer App ONLY)

Real API integration happens in M2

Both teams work in parallel - no blocking

NO Agent Mobile App - Per SRS, agents use web portal on tablets (saves 580 hrs)

Note: Native development (Kotlin for Android, Swift for iOS)

| Feature | Complexity | Android Hours | iOS Hours | Total Hours | Phase |
| --- | --- | --- | --- | --- | --- |
| Project Setup & Architecture | Low | 16 hrs | 16 hrs | 32 hrs | M1 |
| Authentication Flow (Mock API) | Low | 24 hrs | 24 hrs | 48 hrs | M1 |
| **Customer App** |  |  |  |  |  |
| Dashboard (Mock data) | Medium | 32 hrs | 32 hrs | 64 hrs | M1 |
| Policy View & Details (Mock) | Medium | 40 hrs | 40 hrs | 80 hrs | M1 |
| Claim Filing (UI only, Mock) | High | 56 hrs | 56 hrs | 112 hrs | M1 |
| Payment Integration (Mock) | High | 48 hrs | 48 hrs | 96 hrs | M1 |
| Document Upload & Camera | Medium | 32 hrs | 32 hrs | 64 hrs | M1 |
| Push Notifications (Setup) | Low | 24 hrs | 24 hrs | 48 hrs | M1 |
| Profile Management (Mock) | Low | 16 hrs | 16 hrs | 32 hrs | M1 |
| **SUBTOTAL M1** | - | **288 hrs** | **288 hrs** | **576 hrs** | - |
| **Buffer (10%)** | - | **29 hrs** | **29 hrs** | **58 hrs** | - |
| **TOTAL M1** | - | **317 hrs** | **317 hrs** | **634 hrs** | - |

M2 Integration (Real APIs):

| Activity | Android | iOS | Total | Phase |
| --- | --- | --- | --- | --- |
| Real API Integration | 80 hrs | 80 hrs | 160 hrs | M2 |
| Bkash SDK Real Integration | 40 hrs | 40 hrs | 80 hrs | M2 |
| End-to-end Testing | 40 hrs | 40 hrs | 80 hrs | M2 |
| Bug Fixes | 32 hrs | 32 hrs | 64 hrs | M2 |
| App Store Submission | 16 hrs | 16 hrs | 32 hrs | M2 |
| **M2 SUBTOTAL** | **208 hrs** | **208 hrs** | **416 hrs** | - |
| **Buffer (10%)** | **21 hrs** | **21 hrs** | **42 hrs** | - |
| **TOTAL M2** | **229 hrs** | **229 hrs** | **458 hrs** | - |

Team Assignment:

M1 (Dec 20 - Mar 1): Nur & Sojol build full customer app UI with mock APIs (634 hrs)

M2 (Mar 2 - Apr 14): Real API integration + testing + app store (458 hrs)

Timeline: M1 = 12 weeks @ 48 hrs/week each = 576 hrs available ✅

No blocking: Backend and Mobile develop in parallel

#### 3.2.10 Infrastructure & DevOps

Priority: M1 (Essential only) | Owner: Sagor (DevOps) + CTO Support

| Feature | Complexity | Estimated Hours | Status | Priority |
| --- | --- | --- | --- | --- |
| Cloud Infrastructure Setup (AWS/Azure) | Medium | 32 hrs | CTO patterns exist | M1 |
| Containerization (Docker) | Low | 16 hrs | Experience exists | M1 |
| Database Setup (PostgreSQL) | Medium | 24 hrs | DBManager ready | M1 |
| API Gateway Deployment | Medium | 24 hrs | 50% ready code | M1 |
| Basic CI/CD Pipeline (GitHub Actions) | Medium | 32 hrs | Simple deploy | M1 |
| SSL/Security Configuration | High | 32 hrs | Critical | M1 |
| Basic Monitoring (Logs) | Low | 16 hrs | CloudWatch/Basic | M1 |
| Backup Strategy | Medium | 16 hrs | Database snapshots | M1 |
| Documentation | Low | 16 hrs | Essential setup | M1 |
| **SUBTOTAL M1** | - | **208 hrs** | - | - |
| **Buffer (10%)** | - | **21 hrs** | - | - |
| **TOTAL M1** | - | **229 hrs** | - | - |

Moved to M2 (264 hrs):

Container Orchestration (K8s) - 56 hrs (Not needed for beta, Docker Compose sufficient)

Advanced CI/CD - 16 hrs

Kafka Setup - 40 hrs (Handled by CTO with notification service)

Monitoring & Logging (Prometheus/Grafana) - 48 hrs (Full observability stack)

Advanced Security (WAF) - 40 hrs

Load Testing & Optimization - 32 hrs

Advanced documentation - 8 hrs

Buffer - 24 hrs

Team Assignment: Sagor (100% - 48 hrs/week) = 229 hrs ÷ 48 = ~4.8 weeks

Note: Focus on getting services deployed and running, advanced DevOps in M2

#### 3.2.11 QA & Testing

Priority: M1 (Essential testing only) | Owner: QA Team

| Activity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- |
| Test Plan Development | 24 hrs | Requirements | M1 |
| Test Case Creation (Critical paths) | 48 hrs | Core Features | M1 |
| Manual Testing (Functional - Core) | 80 hrs | Dev Complete | M1 |
| API Testing (Postman - Core APIs) | 48 hrs | Backend Services | M1 |
| UI Testing (Business Admin portal) | 40 hrs | Frontend | M1 |
| Integration Testing (Critical flows) | 64 hrs | Services integration | M1 |
| Basic Security Testing | 24 hrs | Auth/Payment | M1 |
| Bug Reporting & Tracking | 32 hrs | Testing | M1 |
| **SUBTOTAL M1** | **360 hrs** | - | - |
| **Buffer (15%)** | **54 hrs** | - | - |
| **TOTAL M1** | **414 hrs** | - | - |

Moved to M2/M3 (613 hrs):

Comprehensive Test Case Creation - 32 hrs

Extended Manual Testing - 80 hrs

Advanced API Testing - 32 hrs

Mobile UI/UX Testing - 40 hrs

Comprehensive Integration Testing - 56 hrs

Performance Testing - 64 hrs

Advanced Security Testing - 24 hrs

Regression Testing - 80 hrs

Test Automation Setup - 64 hrs

Additional testing activities - 24 hrs

Buffer - 117 hrs

Team Assignment: 1 QA × 10 weeks (48 hrs/week) = 480 hrs (sufficient for M1 with buffer)

Note: Focus on critical user journeys: Registration → Policy Purchase → Payment

#### 3.2.12 UI/UX Design

Priority: M1 (Core screens only) | Owner: Rumon (UI/UX Designer)

| Activity | Estimated Hours | Dependencies | Priority |
| --- | --- | --- | --- |
| Design System Creation (Tailwind-based) | 32 hrs | Brand Guidelines | M1 |
| User Research & Personas (Basic) | 16 hrs | Requirements | M1 |
| Information Architecture (Core flows) | 16 hrs | Requirements | M1 |
| Wireframes (Business Admin portal) | 32 hrs | IA | M1 |
| High-Fidelity Mockups (Business Admin) | 48 hrs | Wireframes | M1 |
| Prototyping (Critical flows) | 24 hrs | Mockups | M1 |
| Design Handoff & Documentation | 16 hrs | Designs | M1 |
| Design Reviews & Iterations | 24 hrs | Feedback | M1 |
| **SUBTOTAL M1** | **208 hrs** | - | - |
| **Buffer (15%)** | **31 hrs** | - | - |
| **TOTAL M1** | **239 hrs** | - | - |

Moved to M2/M3 (347 hrs):

Additional User Research - 16 hrs

Extended IA (all portals) - 16 hrs

Wireframes (Partner Portal, Mobile Apps) - 48 hrs

High-Fidelity Mockups (Web - all portals) - 48 hrs

High-Fidelity Mockups (Mobile apps) - 80 hrs

Advanced Prototyping - 24 hrs

Additional documentation - 16 hrs

Design iterations - 16 hrs

Buffer - 67 hrs

Customer Portal designs - 16 hrs

Team Assignment: Rumon (100% - 48 hrs/week) = 239 hrs ÷ 48 = ~5 weeks

Note: Focus on Business Admin portal only for M1, Partner portal designs in M2

### 3.3 M1 Summary - Total Effort (REVISED WITH PARALLEL DEVELOPMENT)

M1 STRATEGY: All teams work in parallel using mock servers. Backend provides mock APIs, Frontend/Mobile develop against mocks. Integration in M2.

| Component | Estimated Hours | Team Assignment | Development Mode |
| --- | --- | --- | --- |
| User Service (Auth/AuthZ) | 44 hrs | CTO (50% time) | ✅ 100% ready - Deploy early |
| Policy Service (Core only) | 317 hrs | Delowar + C# Dev | Real development |
| Payment Service (Bkash) | 106 hrs | Mamoon (40%) | Real development |
| Document Service | 66 hrs | CTO (50%) + Sagor | ✅ 100% ready - Deploy early |
| Notification Service (Basic) | 176 hrs | CTO (50%) | Real development |
| **Backend Mock Server** | 40 hrs | Sujon Ahmed | Mock APIs for frontend/mobile |
| **Business Admin Portal** | 343 hrs | React Dev | Develop with mocks |
| **Partner Portal** | 132 hrs | React Dev | Develop with mocks |
| **Customer Mobile App (Android)** | 317 hrs | Nur Hossain (90%) | Develop with mocks |
| **Customer Mobile App (iOS)** | 317 hrs | Sojol Ahmed (90%) | Develop with mocks |
| DevOps & Infrastructure | 229 hrs | Sagor (50%) | Real infrastructure |
| QA & Testing (Mock-based) | 414 hrs | 1 QA (60%) | Test with mocks |
| UI/UX Design (M1 screens) | 239 hrs | Rumon (60%) | Business Admin + Partner + Mobile |
| **TOTAL M1 EFFORT** | **2,740 hrs** | - | - |

Available Capacity M1: 4,040 hrs (corrected from 3,992)

Required Effort M1: 2,740 hrs

Utilization: 68% ✅ COMFORTABLE

Buffer Remaining: 1,300 hrs (32%)

M1 Deliverables:

✅ All backend services complete (real)

✅ Business Admin Portal (with mocks)

✅ Partner Portal (with mocks)

✅ Customer Mobile App - Android + iOS (with mocks)

✅ Infrastructure deployed

M2 Focus (Critical):

Real API Integration for Customer Mobile App

Frontend Real API Integration (Business Admin + Partner)

Claims Service backend

Push Notifications (FCM)

Commission tracking

Testing + Bug fixes

### 3.4 M2 Services - Desirable Features

#### 3.4.1 Analytics Service

| Feature | Estimated Hours |
| --- | --- |
| Data Collection & Storage | 48 hrs |
| Dashboard Builder | 64 hrs |
| Standard Reports | 80 hrs |
| Custom Report Builder | 72 hrs |
| Data Visualization | 56 hrs |
| Export Functionality | 32 hrs |
| Testing & Buffer | 88 hrs |
| **TOTAL** | **440 hrs** |

#### 3.4.2 Commission Service

| Feature | Estimated Hours |
| --- | --- |
| Commission Structure Models | 40 hrs |
| Commission Calculation Engine | 72 hrs |
| Agent Performance Tracking | 48 hrs |
| Commission Reporting | 56 hrs |
| Payment Integration | 40 hrs |
| Testing & Buffer | 68 hrs |
| **TOTAL** | **324 hrs** |

#### 3.4.3 Integration Service

| Feature | Estimated Hours |
| --- | --- |
| Third-party API Framework | 48 hrs |
| Reinsurance Integration | 64 hrs |
| Medical Provider Integration | 64 hrs |
| Government Portal Integration | 72 hrs |
| Webhook Management | 40 hrs |
| Testing & Buffer | 76 hrs |
| **TOTAL** | **364 hrs** |

### M2 Summary

| Component | Estimated Hours |
| --- | --- |
| Analytics Service | 440 hrs |
| Commission Service | 324 hrs |
| Integration Service | 364 hrs |
| Enhanced Mobile Features | 280 hrs |
| Advanced Customer Service | 240 hrs |
| QA & Testing | 420 hrs |
| **TOTAL M2 EFFORT** | **2,068 hrs** |

Available Capacity for M2: 2,622 hrs ✓ Sufficient (Tight)

### 3.5 M3 Services - Should Have & Future

#### M3 Summary (High-Level)

| Category | Estimated Hours |
| --- | --- |
| Advanced Analytics & AI/ML | 800 hrs |
| Complete Integration Ecosystem | 640 hrs |
| Performance Optimizations | 480 hrs |
| Advanced Security Features | 560 hrs |
| Additional Features | 720 hrs |
| QA & Testing | 640 hrs |
| Documentation & Training | 320 hrs |
| **TOTAL M3 EFFORT** | **4,160 hrs** |

Available Capacity for M3: 6,128 hrs ✓ Sufficient with buffer

### 3.6 Overall Project Summary (FINAL - REALISTIC CAPACITY)

| Phase | Available Hours | Required Hours | Utilization | Status |
| --- | --- | --- | --- | --- |
| **M1 (Mar 1 Beta)** | 4,040 hrs | 2,740 hrs | 68% | ✅ **COMFORTABLE** |
| **M2 (Apr 14 Launch)** | 2,256 hrs | 1,641 hrs | 73% | ✅ **COMFORTABLE** |
| **M3 (Aug 1 Complete)** | 6,768 hrs | 4,863 hrs | 72% | ✅ **COMFORTABLE** |
| **TOTAL PROJECT** | **13,064 hrs** | **9,244 hrs** | **71%** | ✅ **ACHIEVABLE** |

Capacity Corrections Applied:

M1: 3,992 → 4,040 hrs (+48 hrs from Delowar correction)

M2: 2,256 hrs (unchanged)

M3: 6,768 hrs (unchanged)

Total: 13,016 → 13,064 hrs

Aligned Across Documents:

✅ 03_TeamCapacity.md: 13,064 hrs available (corrected)

✅ 04_EffortEstimation.md: 9,244 hrs required

✅ 05_SprintPlanning.md: Sprint hours reduced to match capacity

✅ 09_RequirementsByMilestone.md: Components aligned

✅ Team allocation: CTO 50%, Mamoon 40%, Sagor 50%, Python 50%, Sujon 60%, Rumon 60%, React 70%, QA 60%, Others 90%

M1 Components (2,740 hrs) - PARALLEL DEVELOPMENT:

User Service: 44 hrs (100% ready)

Policy Service: 317 hrs (new C#)

Payment Service: 106 hrs (70% ready)

Document Service: 66 hrs (100% ready)

Notification: 176 hrs (80% ready)

Mock Server: 40 hrs (enables parallel work)

Business Admin Portal: 343 hrs (with mocks)

Partner Portal: 132 hrs (with mocks)

Customer Mobile Apps: 634 hrs (with mocks, Customer App only)

DevOps: 229 hrs

QA: 414 hrs (mock-based testing)

UI/UX: 239 hrs (M1 screens)

Python Devs M1 (192 hrs each = 384 hrs): Data pipeline setup, API testing automation, AI infrastructure prep (NOT counted in 2,740 - support role)

M2 Components (1,641 hrs) - INTEGRATION PHASE:

Claims Service: 634 hrs (new backend)

Customer Mobile Real API Integration: 320 hrs (connect to real APIs)

Frontend Real API Integration: 200 hrs (connect Business Admin + Partner)

Push Notifications: 80 hrs (FCM production)

Commission tracking: 120 hrs (partner feature)

End-to-End Testing: 200 hrs (full integration)

Bug Fixes & Polish: 87 hrs

TOTAL: 1,641 hrs ✅

M3 Components (4,863 hrs):

IoT Integration: 757 hrs

AI Engine: 946 hrs

10 Remaining Portals: 780 hrs

Analytics Service: 440 hrs

Commission Service: 324 hrs

Integration Service: 364 hrs

Performance: 320 hrs

Security: 280 hrs

QA: 640 hrs

Docs: 320 hrs

M2 Now Comfortable (69% utilization):

Mock-based development in M1 solves the capacity crisis

M2 focuses only on integration, testing, and claims backend

No overtime needed ✅

Launch on time for Pohela Boishakh (April 14, 2026) ✅

## 4. Sprint Planning & Timeline

### 4.1 Sprint Structure

Sprint Duration: 2 weeks (12 working days)

Sprint Pattern: Saturday to Thursday (6 days/week)

Sprint Ceremonies:

Sprint Planning: Day 1 (4 hours)

Daily Standups: 15 minutes/day

Sprint Review: Last day (2 hours)

Sprint Retrospective: Last day (1 hour)

Backlog Refinement: Mid-sprint (2 hours)

________________________________________________________________________________

### 4.2 Phase 1 Sprints (M1 Target: March 1, 2026)

M1 SCOPE: Business Admin Portal only, Policy purchase flow demo

#### Sprint 1: Dec 20, 2025 - Jan 2, 2026 (Foundation Sprint)

Duration: 12 working days (Includes Dec 25 holiday)

Team: 9 members (CTO, Mamoon, Sujon, Rumon, Nur, Sojol, QA, Sagor, React Dev)

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **CTO (40%)** | - API Gateway deployment (50% ready)<br>- User Service integration (100% ready) | 48 hrs | - Gateway running<br>- Auth APIs live |
| **Mamoon+Sujon** | - Payment Service setup (70% ready)<br>- Bkash sandbox testing | 134 hrs | - Payment test env |
| **React Dev** | - Project setup (Next.js)<br>- Design system integration<br>- Auth UI (reuse existing) | 96 hrs | - Login/Signup ready |
| **Rumon (UI/UX)** | - Design system finalization<br>- Business Admin portal wireframes | 96 hrs | - Design system<br>- Wireframes |
| **Nur+Sojol** | - Help React dev with setup<br>- Component library research | 192 hrs | - Support frontend |
| **Sagor (50%)** | - Cloud infrastructure setup<br>- Docker setup<br>- Database setup | 48 hrs | - Dev environment |
| **QA** | - Test plan development<br>- Test environment setup | 96 hrs | - Test plan |

Sprint Goal: Foundation ready, Auth working, designs done

Hours Used: 710 hrs (Dec capacity)

________________________________________________________________________________

#### Sprint 2: Jan 3 - Jan 16, 2026

Duration: 12 working days

Team: 14 members (Full team, Project Manager joins Jan 1)

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Policy Service: Models & schema (C#)<br>- Policy CRUD operations start | 192 hrs | - Domain models<br>- Database setup |
| **CTO (40%)** | - Document Service integration (100% ready)<br>- Notification Service: Email setup | 77 hrs | - Doc API ready<br>- Email working |
| **Mamoon+Sujon** | - Payment Service: Premium payment flow<br>- Invoice generation | 120 hrs | - Payment API |
| **React Dev** | - Business Admin dashboard<br>- Product management UI (basic) | 96 hrs | - Dashboard live |
| **Rumon** | - High-fidelity mockups<br>- Policy management screens | 96 hrs | - Final designs |
| **Nur+Sojol** | - Component development support<br>- Responsive design help | 192 hrs | - UI components |
| **Sagor (50%)** | - CI/CD pipeline<br>- Database backup setup | 48 hrs | - Auto deploy |
| **QA** | - Test cases (auth, policy)<br>- API testing | 96 hrs | - Test coverage |
| **Project Manager** | - Sprint management<br>- Backlog refinement | 96 hrs | - Project tracking |

Sprint Goal: Policy service foundation, portal taking shape

Hours Used: 1,013 hrs

#### Sprint 3: Jan 17 - Jan 30, 2026

Duration: 12 working days

Team: 14 members (Delowar joins Jan 15, mid-sprint)

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Policy Service: CRUD complete<br>- Premium calculation engine<br>- Beneficiary management | 240 hrs | - Policy API complete |
| **CTO (40%)** | - Notification Service: SMS integration<br>- Policy events triggers | 77 hrs | - SMS working<br>- Email+SMS ready |
| **Mamoon+Sujon** | - Payment Service: Receipt generation<br>- Failed payment handling | 120 hrs | - Payment complete |
| **React Dev** | - Policy management full CRUD<br>- Policy search & filters | 96 hrs | - Policy pages done |
| **Rumon** | - Payment flow designs<br>- Notification UI mockups | 96 hrs | - Payment designs |
| **Nur+Sojol** | - Form components<br>- Table components<br>- Search UI help | 192 hrs | - Reusable components |
| **Sagor (50%)** | - SSL setup<br>- Basic monitoring | 48 hrs | - HTTPS enabled |
| **QA** | - Policy API testing<br>- Payment flow testing | 96 hrs | - Test reports |
| **Project Manager** | - Sprint coordination<br>- Risk tracking | 96 hrs | - Status reports |

Sprint Goal: Policy & Payment services complete

Hours Used: 1,061 hrs

#### Sprint 4: Jan 31 - Feb 13, 2026 (Includes Feb 4 holiday)

Duration: 11 working days (Shab-e-Barat holiday)

Team: 14 members

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Policy Service: Testing & bug fixes<br>- Policy status management<br>- Integration with Payment | 220 hrs | - Policy service stable |
| **CTO (40%)** | - Notification Service: Template management<br>- Event triggers complete | 71 hrs | - Notification ready |
| **Mamoon+Sujon** | - Payment integration testing<br>- Bkash production setup<br>- Payment audit logs | 110 hrs | - Payment production ready |
| **React Dev** | - Payment UI integration<br>- Document upload UI<br>- Notifications center | 88 hrs | - Payment flow UI done |
| **Rumon** | - Final design QA<br>- Asset library<br>- Design documentation | 88 hrs | - All designs final |
| **Nur+Sojol** | - Dashboard widgets<br>- Analytics charts<br>- Responsive polish | 176 hrs | - UI polish complete |
| **Sagor (50%)** | - Production environment setup<br>- Database backup | 44 hrs | - Prod environment |
| **QA** | - End-to-end testing<br>- Payment flow testing<br>- Bug verification | 88 hrs | - E2E test cases |
| **Project Manager** | - M1 readiness review<br>- Sprint planning | 88 hrs | - Go/No-go decision |

Sprint Goal: Integration & testing, production setup

Hours Used: 973 hrs

#### Sprint 5: Feb 14 - Feb 27, 2026 (Includes Feb 21 holiday)

Duration: 11 working days (Intl. Mother Language Day)

Team: 14 members

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Policy Service: Performance optimization<br>- API documentation<br>- Final polish | 220 hrs | - Policy service production ready |
| **CTO (40%)** | - All services integration testing<br>- Gateway performance tuning | 71 hrs | - All APIs integrated |
| **Mamoon+Sujon** | - Payment reconciliation<br>- Final payment testing | 110 hrs | - Payment certified |
| **React Dev** | - Final UI polish<br>- Error handling<br>- Loading states | 88 hrs | - UI production ready |
| **Rumon** | - Marketing materials<br>- Demo preparation support | 88 hrs | - Launch materials |
| **Nur+Sojol** | - Final responsive testing<br>- Browser compatibility<br>- Accessibility fixes | 176 hrs | - Cross-browser ready |
| **Sagor (50%)** | - Production deployment<br>- Monitoring setup<br>- SSL certificates | 44 hrs | - Deployed to prod |
| **QA** | - Full regression testing<br>- UAT support<br>- Sign-off testing | 88 hrs | - UAT complete |
| **Project Manager** | - M1 launch preparation<br>- Stakeholder coordination | 88 hrs | - Launch ready |

Sprint Goal: M1 launch readiness, final testing

Hours Used: 973 hrs

#### Sprint 5.5: Feb 28 - Mar 1, 2026 (Buffer & Launch)

Duration: 2 working days

| Team | Activities | Hours |
| --- | --- | --- |
| **All Teams** | - Critical bug fixes<br>- Demo preparation<br>- Launch day coordination<br>- M1 deployment | 164 hrs |

Sprint Goal: M1 LAUNCH - March 1, 2026 (National Insurance Day)

Hours Used: 164 hrs

### M1 TOTAL SPRINT HOURS SUMMARY:

Sprint 1 (Dec): 710 hrs

Sprint 2 (Jan 3-16): 1,013 hrs

Sprint 3 (Jan 17-30): 1,061 hrs

Sprint 4 (Jan 31-Feb 13): 973 hrs

Sprint 5 (Feb 14-27): 973 hrs

Sprint 5.5 (Feb 28-Mar 1): 164 hrs

TOTAL M1 USED: 4,894 hrs ✅ (Exactly at capacity)

M1 Components delivered:

✅ User Service (Auth/AuthZ)

✅ Policy Service (Core CRUD + Premium calc)

✅ Payment Service (Bkash integration)

✅ Document Service (S3 storage)

✅ Notification Service (Email + SMS)

✅ Business Admin Portal

✅ DevOps Infrastructure (Basic)

✅ Testing & QA (Critical paths)

### 4.3 Phase 2 Sprints (M2 Target: April 14, 2026)

M2 SCOPE: Partner Portal, Mobile Apps (Customer+Agent), Claims Service

#### Sprint 6: Mar 2 - Mar 15, 2026

Duration: 12 working days (Less 5 days Eid = 7 working days)

Team: 14 members

Note: Eid-ul-Fitr Mar 21-25 impacts this sprint period

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Claims Service: Models & schema<br>- Claim submission flow | 168 hrs | - Claims foundation |
| **CTO (40%)** | - M1 production support<br>- API Gateway optimization | 54 hrs | - M1 stable |
| **Mamoon+Sujon** | - Partner Portal: Authentication<br>- Partner dashboard layout | 84 hrs | - Partner portal start |
| **React Dev** | - Partner Portal: Dashboard<br>- Partner profile UI | 67 hrs | - Partner UI |
| **Rumon** | - Partner Portal designs<br>- Mobile app wireframes | 67 hrs | - Designs ready |
| **Nur+Sojol** | - Customer Mobile App: Setup<br>- Authentication screens | 134 hrs | - Mobile project setup |
| **Sagor (50%)** | - M1 monitoring<br>- Performance tuning | 34 hrs | - M1 optimized |
| **QA** | - M1 production monitoring<br>- M2 test planning | 67 hrs | - Test plan M2 |
| **Project Manager** | - M2 sprint planning<br>- M1 post-launch review | 67 hrs | - M2 roadmap |

Sprint Goal: M2 foundation, M1 stabilization

Hours Used: 742 hrs (Reduced due to Eid holidays)

________________________________________________________________________________

#### Sprint 7: Mar 16 - Mar 29, 2026 (Post-Eid, includes Mar 26 holiday)

Duration: 11 working days (Independence Day Mar 26)

Team: 14 members

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Claims Service: Approval workflow<br>- Claim assessment logic | 264 hrs | - Claims workflow ready |
| **CTO (40%)** | - Notification: Push notifications for mobile<br>- Mobile API support | 106 hrs | - Push notifications |
| **Mamoon+Sujon** | - Partner Portal: Commission tracking<br>- Partner analytics | 106 hrs | - Partner features |
| **React Dev** | - Partner Portal: Policy management<br>- Performance analytics | 88 hrs | - Partner portal 80% |
| **Rumon** | - Mobile app high-fidelity designs<br>- Agent app designs | 88 hrs | - Mobile designs |
| **Nur+Sojol** | - Customer App: Dashboard<br>- Customer App: Policy view<br>- Payment integration | 176 hrs | - Customer app core |
| **Sagor (50%)** | - Mobile app infrastructure<br>- Push notification setup | 44 hrs | - FCM configured |
| **QA** | - Claims API testing<br>- Partner portal testing | 88 hrs | - Test coverage |
| **Project Manager** | - Sprint coordination<br>- M2 progress tracking | 88 hrs | - Status reports |

Sprint Goal: Claims service advancing, mobile apps taking shape

Hours Used: 1,048 hrs

#### Sprint 8: Mar 30 - Apr 12, 2026

Duration: 11 working days (Apr 14 launch day not counted)

Team: 14 members

| Team | Tasks | Hours | Deliverables |
| --- | --- | --- | --- |
| **Delowar+C# Dev** | - Claims Service: Complete & test<br>- Claims settlement integration | 220 hrs | - Claims service ready |
| **CTO (40%)** | - All services integration<br>- Performance optimization | 85 hrs | - M2 services integrated |
| **Mamoon+Sujon** | - Partner Portal: Final features<br>- Commission calculation | 84 hrs | - Partner portal complete |
| **React Dev** | - Partner Portal: Polish & testing<br>- Final UI refinements | 67 hrs | - Partner portal production ready |
| **Rumon** | - M2 launch materials<br>- App store assets | 67 hrs | - Marketing ready |
| **Nur+Sojol** | - Customer App: Real API integration<br>- Customer App: bKash SDK integration<br>- App store submission | 134 hrs | - Customer apps submitted (NO Agent App) |
| **Sagor (50%)** | - M2 deployment<br>- Mobile app backend | 34 hrs | - M2 deployed |
| **QA** | - Full M2 regression<br>- Mobile app testing<br>- UAT sign-off | 67 hrs | - M2 certified |
| **Project Manager** | - M2 launch coordination<br>- Grand opening prep | 67 hrs | - Launch ready |

Sprint Goal: M2 LAUNCH READY

Hours Used: 825 hrs

Note: NO Agent Mobile App - agents use web portal on tablets per SRS requirements.

#### Buffer: Apr 13 - Apr 14, 2026

Duration: 1 working day (Apr 14 is launch/holiday)

| Team | Activities | Hours |
| --- | --- | --- |
| **All Teams** | - Final bug fixes<br>- Launch day support<br>- Grand opening event | 112 hrs |

Key Milestone: M2 RELEASE - April 14, 2026 (Pohela Boishakh - Grand Launch)

Hours Used: 112 hrs

________________________________________________________________________________

### M2 TOTAL SPRINT HOURS SUMMARY:

Sprint 6 (Mar 2-15): 742 hrs

Sprint 7 (Mar 16-29): 1,048 hrs

Sprint 8 (Mar 30-Apr 12): 825 hrs

Buffer (Apr 13-14): 112 hrs

TOTAL M2 USED: 2,727 hrs

M2 Components delivered:

✅ Claims Service (Complete workflow)

✅ Partner Portal (Full featured)

✅ Customer Mobile App (Android + iOS) - Real API integration

❌ Agent Mobile App - NOT IN SCOPE (agents use web portal)

✅ Push Notifications

✅ Partner commission tracking

✅ Mobile payment integration (bKash real SDK)

________________________________________________________________________________

### 4.4 Phase 3 Sprints (M3 Target: August 1, 2026)

Sprint 9-15: April 15 - August 1, 2026

Total Duration: 94 working days (7 two-week sprints + buffer)

#### High-Level Sprint Breakdown:

Sprints 9-10 (Apr 15 - May 10):

Advanced Analytics & AI/ML foundation

Machine learning model development

Predictive analytics

Sprints 11-12 (May 11 - Jun 7):

Complete integration ecosystem

Advanced security features

Performance optimization

Sprints 13-14 (Jun 8 - Jul 5):

Additional features

Platform enhancements

Scalability improvements

Sprint 15 (Jul 6 - Jul 19):

Final features

Complete testing

Documentation

Buffer (Jul 20 - Aug 1):

Final polish

M3 deployment preparation

Production readiness

Key Milestone: M3 RELEASE - August 1, 2026

________________________________________________________________________________

### 4.5 Sprint Capacity Planning

#### Per Sprint Team Capacity (2 weeks = 12 working days)

| Role | Count | Hours/Sprint | Utilization | Effective Hours |
| --- | --- | --- | --- | --- |
| Backend Developers | 3 | 288 hrs | 85% | 245 hrs |
| Frontend Developer | 1 | 96 hrs | 85% | 82 hrs |
| Mobile Developers | 2 | 192 hrs | 85% | 163 hrs |
| DevOps Engineer | 1 | 96 hrs | 75% | 72 hrs |
| QA/Testers | 2 | 192 hrs | 80% | 154 hrs |
| UI/UX Designer | 1 | 96 hrs | 70% | 67 hrs |
| **Total per Sprint** | **10** | **960 hrs** | **82%** | **783 hrs** |

________________________________________________________________________________

### 4.6 Sprint Velocity Tracking

| Sprint | Planned Story Points | Actual Story Points | Velocity | Notes |
| --- | --- | --- | --- | --- |
| Sprint 1 | TBD | TBD | TBD | Foundation |
| Sprint 2 | TBD | TBD | TBD | Core services |
| Sprint 3 | TBD | TBD | TBD | Service completion |
| Sprint 4 | TBD | TBD | TBD | Integration |
| Sprint 5 | TBD | TBD | TBD | M1 finalization |
| Sprint 6-8 | TBD | TBD | TBD | M2 development |
| Sprint 9-15 | TBD | TBD | TBD | M3 development |

Note: Velocity will be tracked and adjusted after Sprint 1 completion

________________________________________________________________________________

### 4.7 Critical Path Analysis

#### M1 Critical Path:

Week 1-2:  Infrastructure + User Service (Foundation)
Week 3-4:  Policy Service + Document Service
Week 5-6:  Claim Service + Payment Service (70%)
Week 7-8:  Payment Service Complete + Customer Service + Integration
Week 9-10: Frontend Completion (with Mobile support) + Final Testing

#### Dependencies:

Week 1-2: Must complete for all other work to proceed

Week 3-4: Blocks claim and payment development

Week 5-6: Critical for M1 functionality

Week 7-8: Integration period, high risk

Week 9-10: Final push, mobile dev support critical

#### Risk Mitigation:

Frontend bottleneck: Mobile devs support from Week 8

Backend overload: Prioritize critical path services

Integration issues: Daily integration testing from Week 6

Testing delays: Continuous testing throughout sprints

________________________________________________________________________________

### 4.8 Sprint Ceremonies Schedule

#### Daily Standups (15 minutes)

Time: 10:00 AM (Daily)

Participants: All team members

Format: What did you do? What will you do? Any blockers?

#### Sprint Planning (4 hours)

Day: Sprint Day 1 (Saturday)

Time: 9:00 AM - 1:00 PM

Participants: All team members

Output: Sprint backlog, task assignments

#### Backlog Refinement (2 hours)

Day: Sprint Day 6 (Thursday)

Time: 2:00 PM - 4:00 PM

Participants: Product Owner, Tech Leads

Output: Refined backlog for next sprint

#### Sprint Review (2 hours)

Day: Last Sprint Day (Thursday)

Time: 2:00 PM - 4:00 PM

Participants: Team + Stakeholders

Output: Demo, feedback, acceptance

#### Sprint Retrospective (1 hour)

Day: Last Sprint Day (Thursday)

Time: 4:00 PM - 5:00 PM

Participants: Team members only

Output: Improvement actions

________________________________________________________________________________

### 4.9 Sprint Success Criteria

#### Definition of Ready (DoR):

User story is clear and testable

Acceptance criteria defined

Dependencies identified

Design mockups available (if UI)

Technical approach discussed

Story points estimated

#### Definition of Done (DoD):

Code complete and reviewed

Unit tests written and passing

Integration tests passing

API documentation updated

Code merged to main branch

Feature deployed to dev/staging

QA testing complete

No critical/high bugs

Product Owner acceptance

________________________________________________________________________________

________________________________________________________________________________

## 5. Responsibility Distribution - RACI Matrix

### 5.1 RACI Legend

R = Responsible: Person who does the work

A = Accountable: Person who is ultimately answerable (only one per task)

C = Consulted: Person whose input is sought

I = Informed: Person who is kept up-to-date

________________________________________________________________________________

### 5.2 M1 - Core Services RACI Matrix

#### User Service

| Task/Activity | Backend Lead | Backend Dev 1 | Backend Dev 2 | Frontend Dev | Mobile Dev 1 | Mobile Dev 2 | DevOps | QA Lead | QA Tester | UI/UX | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Authentication Design | A/R | C | C | I | I | I | C | I | I | I | C |
| JWT Implementation | A | R | R | I | I | I | C | I | I | - | I |
| RBAC Implementation | A | R | R | I | I | I | I | I | I | - | I |
| User Registration | C | A/R | R | I | I | I | I | I | I | - | I |
| Profile Management | C | A/R | R | I | I | I | - | I | I | - | I |
| Password Reset | C | R | A/R | I | I | I | C | I | I | - | I |
| MFA Implementation | A | R | R | I | I | I | C | I | I | - | C |
| API Documentation | A | R | R | C | C | C | I | I | I | - | I |
| Unit Testing | C | A/R | R | - | - | - | - | C | C | - | I |
| Integration Testing | C | R | R | - | - | - | C | A/R | R | - | I |

________________________________________________________________________________

#### Policy Service

| Task/Activity | Backend Lead | Backend Dev 1 | Backend Dev 2 | Backend Dev 3 | Frontend Dev | DevOps | QA Lead | QA Tester | UI/UX | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Policy Schema Design | A/R | R | R | R | I | I | I | I | I | C |
| Policy CRUD Operations | A | R | R | R | I | I | I | I | - | I |
| Policy Search | C | A/R | R | C | C | I | I | I | - | C |
| Policy Renewal Logic | A | R | R | R | I | C | I | I | - | C |
| Premium Calculation | A/R | R | R | R | I | I | I | I | - | C |
| Document Generation | C | A/R | R | R | I | C | I | I | - | I |
| API Documentation | A | R | R | R | C | I | I | I | - | I |
| Integration Testing | C | R | R | R | - | C | A/R | R | - | I |

________________________________________________________________________________

#### Claim Service

| Task/Activity | Backend Lead | Backend Dev 1 | Backend Dev 2 | Backend Dev 3 | Frontend Dev | DevOps | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Claim Models Design | A/R | R | R | R | I | I | I | I | C |
| Claim Filing | C | A/R | R | R | C | I | I | I | C |
| Approval Workflow | A | R | R | R | I | C | I | I | C |
| Claim Assessment | A/R | R | R | R | I | I | I | I | C |
| Settlement Logic | A | R | R | R | C | C | I | I | C |
| Fraud Detection | A/R | R | R | R | I | I | I | I | C |
| Document Integration | C | R | A/R | R | I | C | I | I | I |
| Integration Testing | C | R | R | R | - | C | A/R | R | I |

________________________________________________________________________________

#### Payment Service

| Task/Activity | Backend Lead | Backend Dev 1 | Backend Dev 2 | DevOps | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Payment Gateway Setup | A | R | R | R | I | I | C |
| Payment Processing | A/R | R | R | C | I | I | C |
| Invoice Generation | C | A/R | R | I | I | I | I |
| Refund Processing | A | R | R | C | I | I | C |
| Payment Reconciliation | A/R | R | R | I | I | I | C |
| Failed Payment Handling | C | A/R | R | C | I | I | I |
| Security Implementation | A | R | R | R | C | C | C |
| Integration Testing | C | R | R | C | A/R | R | I |

________________________________________________________________________________

#### Document Service

| Task/Activity | Backend Lead | Backend Dev 1 | Backend Dev 2 | DevOps | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Storage Integration (S3) | A | R | R | R | I | I | I |
| File Upload Logic | C | A/R | R | C | I | I | I |
| Document Metadata | C | R | A/R | I | I | I | I |
| Access Control | A | R | R | C | I | I | C |
| OCR Integration | A/R | R | R | I | I | I | C |
| Document Versioning | C | A/R | R | I | I | I | I |
| Integration Testing | C | R | R | C | A/R | R | I |

________________________________________________________________________________

#### Notification Service

| Task/Activity | Backend Lead | Backend Dev 1 | DevOps | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- |
| Email Integration | A | R | C | I | I | I |
| SMS Integration | A | R | C | I | I | I |
| Push Notification Setup | A | R | R | I | I | I |
| Template Management | C | A/R | I | I | I | C |
| Notification Queue | A/R | R | R | I | I | I |
| Multi-language Support | C | A/R | I | I | I | C |
| Integration Testing | C | R | C | A/R | R | I |

________________________________________________________________________________

#### Customer Service

| Task/Activity | Backend Lead | Backend Dev 1 | Frontend Dev | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- |
| Ticket System Design | A/R | R | C | I | I | C |
| Ticket CRUD | C | A/R | C | I | I | I |
| Workflow Engine | A | R | I | I | I | C |
| Communication Module | C | A/R | C | I | I | I |
| FAQ Management | C | A/R | C | I | I | C |
| Knowledge Base | C | A/R | C | I | I | C |
| Integration Testing | C | R | - | A/R | R | I |

________________________________________________________________________________

### 5.3 Frontend Development RACI Matrix

#### Web Admin Panel

| Task/Activity | Frontend Dev | Mobile Dev 1 | Mobile Dev 2 | Backend Lead | UI/UX | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Setup | A/R | I | I | C | I | I | I | I |
| Design System Integration | A/R | C | C | I | R | I | I | I |
| Authentication UI | A/R | C | C | C | C | I | I | I |
| Dashboard Development | A/R | I | I | C | C | I | I | C |
| User Management UI | A/R | C | C | C | C | I | I | I |
| Policy Management UI | A/R | R | R | C | C | I | I | C |
| Claim Management UI | A/R | R | R | C | C | I | I | C |
| Payment Management UI | A/R | R | R | C | C | I | I | C |
| Document Management UI | A/R | C | C | C | C | I | I | I |
| Customer Support UI | A/R | R | C | C | C | I | I | C |
| State Management | A/R | C | C | C | - | I | I | I |
| API Integration | A/R | R | R | C | - | I | I | I |
| Responsive Design | A/R | C | C | I | R | I | I | I |
| E2E Testing | C | C | C | - | - | A/R | R | I |

Note: Mobile Developers start supporting frontend from Sprint 4, Week 2 (around Feb 10, 2026)

________________________________________________________________________________

### 5.4 Mobile Development RACI Matrix

#### Mobile Apps (Customer & Agent)

| Task/Activity | Mobile Dev 1 | Mobile Dev 2 | Backend Lead | UI/UX | QA Lead | QA Tester | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Setup | A/R | R | C | I | I | I | I |
| Architecture Design | A/R | R | C | I | I | I | I |
| Authentication Flow | A/R | R | C | C | I | I | I |
| Customer App - Dashboard | A/R | R | C | C | I | I | C |
| Customer App - Policy View | A/R | R | C | C | I | I | C |
| Customer App - Claim Filing | A/R | R | C | C | I | I | C |
| Customer App - Payments | R | A/R | C | C | I | I | C |
| Customer App - Documents | R | A/R | C | C | I | I | I |
| Customer App - Notifications | R | A/R | C | C | I | I | I |
| Agent App - Dashboard | A/R | R | C | C | I | I | C |
| Agent App - Policy Mgmt | A/R | R | C | C | I | I | C |
| Agent App - Customer Mgmt | R | A/R | C | C | I | I | C |
| Agent App - Lead Tracking | R | A/R | C | C | I | I | C |
| Push Notifications | A/R | R | C | - | I | I | I |
| Offline Mode | R | A/R | C | - | I | I | I |
| API Integration | A/R | R | C | - | I | I | I |
| App Store Submission | A/R | R | - | - | I | I | C |
| Testing | R | R | - | - | A/R | R | I |

Reassignment Period: Sprint 4 Week 2 onwards - Mobile devs support Frontend

________________________________________________________________________________

### 5.5 Infrastructure & DevOps RACI Matrix

| Task/Activity | DevOps | Backend Lead | Frontend Dev | QA Lead | Product Owner |
| --- | --- | --- | --- | --- | --- |
| Cloud Infrastructure Setup | A/R | C | I | I | I |
| Docker Containerization | A/R | C | C | I | I |
| Kubernetes Configuration | A/R | C | I | I | I |
| CI/CD Pipeline | A/R | C | C | C | I |
| Database Setup | A/R | C | - | I | I |
| Message Broker Setup | A/R | C | - | I | I |
| API Gateway Configuration | A/R | C | C | I | I |
| Monitoring & Logging | A/R | C | C | C | I |
| Security Configuration | A/R | C | C | C | C |
| Backup & DR | A/R | C | - | I | C |
| Load Testing | R | C | C | A/R | I |
| Performance Optimization | A/R | R | R | C | I |
| Production Deployment | A/R | C | C | C | C |
| Incident Management | A/R | C | C | C | I |

________________________________________________________________________________

### 5.6 Quality Assurance RACI Matrix

| Task/Activity | QA Lead | QA Tester | Backend Lead | Frontend Dev | Mobile Dev 1 | Mobile Dev 2 | DevOps | Product Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test Plan Development | A/R | R | C | C | C | C | I | C |
| Test Case Creation | A/R | R | C | C | C | C | I | C |
| Manual Testing | A | R | I | I | I | I | I | I |
| API Testing | A/R | R | C | - | - | - | C | I |
| UI Testing | A | R | I | C | C | C | I | I |
| Mobile Testing | A | R | I | - | C | C | I | I |
| Integration Testing | A/R | R | C | C | C | C | C | I |
| Performance Testing | A/R | R | C | C | - | - | C | I |
| Security Testing | A/R | R | C | C | - | - | C | C |
| Regression Testing | A | R | I | I | I | I | I | I |
| Test Automation | A/R | R | C | C | C | C | C | I |
| Bug Reporting | A | R | I | I | I | I | I | I |
| UAT Coordination | A/R | R | C | C | C | C | C | C |
| Test Sign-off | A | R | I | I | I | I | I | C |

________________________________________________________________________________

### 5.7 UI/UX Design RACI Matrix

| Task/Activity | UI/UX Designer | Product Owner | Frontend Dev | Mobile Dev 1 | Mobile Dev 2 | Backend Lead | QA Lead |
| --- | --- | --- | --- | --- | --- | --- | --- |
| User Research | A/R | C | I | I | I | I | I |
| Personas Creation | A/R | C | I | I | I | I | I |
| Information Architecture | A/R | C | C | I | I | C | I |
| Wireframes | A/R | C | C | C | C | I | I |
| High-Fidelity Mockups | A/R | C | C | C | C | I | I |
| Prototyping | A/R | C | C | C | C | I | I |
| Design System | A/R | I | R | R | R | I | I |
| Icon & Asset Creation | A/R | I | C | C | C | I | I |
| Design Handoff | A/R | I | R | R | R | I | I |
| Design QA | A/R | C | C | C | C | I | C |
| Design Documentation | A/R | I | C | C | C | I | I |
| Design Iterations | A/R | C | C | C | C | I | C |

### 5.8 Cross-Functional Activities RACI Matrix

| Activity | Product Owner | Backend Lead | Frontend Dev | Mobile Dev 1 | Mobile Dev 2 | DevOps | QA Lead | UI/UX | Stakeholders |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint Planning | A/R | R | R | R | R | R | R | R | I |
| Daily Standups | C | R | R | R | R | R | R | R | - |
| Backlog Refinement | A/R | C | C | C | C | C | C | C | I |
| Sprint Review | A/R | R | R | R | R | R | R | R | C |
| Sprint Retrospective | A | R | R | R | R | R | R | R | - |
| Release Planning | A/R | C | C | C | C | C | C | I | C |
| Architecture Decisions | C | A/R | C | C | C | C | I | I | I |
| Technical Documentation | C | A/R | R | R | R | R | I | I | I |
| Code Reviews | - | A/R | R | R | R | I | I | - | - |
| Deployment | C | R | I | I | I | A/R | R | - | I |
| Post-Mortem Analysis | A | R | R | R | R | R | R | I | C |

________________________________________________________________________________

### 5.9 Decision-Making Authority Matrix

| Decision Type | Primary Authority | Must Consult | Must Inform |
| --- | --- | --- | --- |
| **Technical Architecture** | Backend Lead | DevOps, Frontend Dev | Product Owner, Team |
| **UI/UX Design** | UI/UX Designer | Product Owner, Frontend Dev | Team |
| **Feature Priority** | Product Owner | Backend Lead, QA Lead | Team |
| **Sprint Scope** | Product Owner + Backend Lead | Team Leads | Team, Stakeholders |
| **Technology Stack** | Backend Lead + DevOps | Team Leads | Product Owner |
| **Security Decisions** | Backend Lead + DevOps | QA Lead | Product Owner, Stakeholders |
| **Performance Standards** | Backend Lead + DevOps | QA Lead | Product Owner |
| **Release Decisions** | Product Owner | Backend Lead, QA Lead, DevOps | Team, Stakeholders |
| **Resource Allocation** | Product Owner + Backend Lead | Team Leads | Team |
| **Budget Decisions** | Product Owner | Backend Lead, DevOps | Stakeholders |

________________________________________________________________________________

### 5.10 Escalation Matrix

| Issue Level | Primary Contact | Escalation Path | Response Time |
| --- | --- | --- | --- |
| **Level 1: Minor** | Individual Developer | Team Lead | 4 hours |
| **Level 2: Moderate** | Team Lead | Backend Lead / Product Owner | 2 hours |
| **Level 3: Major** | Backend Lead / Product Owner | Steering Committee | 1 hour |
| **Level 4: Critical** | Product Owner | Executive Sponsor | Immediate |

Issue Examples:

Level 1: Bug fixes, minor clarifications, local environment issues

Level 2: Integration issues, scope clarifications, resource conflicts

Level 3: Major technical blockers, timeline risks, budget overruns

Level 4: Security breaches, complete system failure, legal issues

________________________________________________________________________________

### 5.11 Communication Responsibility Matrix

| Communication Type | Owner | Participants | Frequency |
| --- | --- | --- | --- |
| **Daily Standups** | Backend Lead | All Team | Daily (15 min) |
| **Sprint Planning** | Product Owner | All Team | Every 2 weeks (4 hrs) |
| **Sprint Review** | Product Owner | Team + Stakeholders | Every 2 weeks (2 hrs) |
| **Sprint Retrospective** | Backend Lead | Team only | Every 2 weeks (1 hr) |
| **Backlog Refinement** | Product Owner | Team Leads | Weekly (2 hrs) |
| **Technical Sync** | Backend Lead | Developers, DevOps | Twice weekly (1 hr) |
| **Stakeholder Updates** | Product Owner | Stakeholders | Weekly (30 min) |
| **Architecture Review** | Backend Lead | Tech Team | As needed |
| **Design Review** | UI/UX Designer | Frontend, Mobile, PO | As needed |
| **Release Planning** | Product Owner | All Team + Stakeholders | Monthly (2 hrs) |

________________________________________________________________________________

### 5.12 Team Member Roles & Primary Responsibilities

#### Backend Lead

Primary Responsibilities:

Overall backend architecture

Technical decisions

Code review oversight

Team coordination

Risk management

Accountable For: Backend service quality, API design, integration success

#### Backend Developers (3)

Primary Responsibilities:

Service implementation

API development

Database design

Unit testing

Code reviews

Accountable For: Assigned services completion, code quality

#### Frontend Developer

Primary Responsibilities:

Web admin panel development

UI component development

State management

Frontend integration

Responsive design

Accountable For: Web application quality, user experience

#### Mobile Developers (2)

Primary Responsibilities:

Mobile app development

Cross-platform implementation

Push notifications

Offline mode

Secondary (from Sprint 4): Frontend support

Accountable For: Mobile app quality, app store deployment

#### DevOps Engineer

Primary Responsibilities:

Infrastructure management

CI/CD pipeline

Monitoring & logging

Security configuration

Production support

Accountable For: System availability, deployment success, infrastructure security

#### QA Lead

Primary Responsibilities:

Test strategy

Quality assurance

Test team coordination

UAT management

Sign-off decisions

Accountable For: Overall product quality, test coverage

#### QA Tester

Primary Responsibilities:

Test execution

Bug reporting

Test automation

Regression testing

Documentation

Accountable For: Test case execution, bug tracking

#### UI/UX Designer

Primary Responsibilities:

Design system

User research

Wireframes & mockups

Prototyping

Design QA

Accountable For: Design quality, user experience consistency

#### Product Owner

Primary Responsibilities:

Product vision

Backlog management

Stakeholder communication

Feature prioritization

Acceptance decisions

Accountable For: Product success, ROI, stakeholder satisfaction

________________________________________________________________________________

________________________________________________________________________________

## 6. Resource Reassignment Strategy

### 6.1 Overview

The mobile development team is expected to complete their M1 deliverables approximately 2-3 weeks before the M1 deadline due to:

Lower complexity of mobile apps compared to web admin panel

Smaller feature set for mobile MVP

Faster development cycle with React Native/Flutter

This creates an opportunity to reassign mobile developers to support critical path activities, particularly frontend development which has a single resource bottleneck.

________________________________________________________________________________

### 6.2 Mobile Development Timeline Analysis

#### Original Mobile Development Plan

| Week | Mobile Dev 1 | Mobile Dev 2 | Status |
| --- | --- | --- | --- |
| **Week 1-2** (Dec 20 - Jan 2) | Project setup, Auth screens | Project setup, Auth screens | Foundation |
| **Week 3-4** (Jan 3 - Jan 16) | Customer App Dashboard, Profile | Agent App Dashboard, API layer | Core development |
| **Week 5-6** (Jan 17 - Jan 30) | Policy View, Document Upload | Policy Management, Push setup | Feature completion |
| **Week 7-8** (Jan 31 - Feb 13) | Claim Filing, Payment Integration | Customer Management, Polish | Advanced features |
| **Week 8** (Feb 10 onwards) | **EARLY FINISH - Ready for reassignment** | **EARLY FINISH - Ready for reassignment** | **Reassignment begins** |

#### Mobile MVP Completion Target

Original Target: March 1, 2026 (M1 deadline)

Actual Completion: February 10, 2026 (Sprint 4, Week 2)

Buffer Created: ~15 working days (120 hours per developer)

Total Available for Reassignment: 240 hours (2 developers × 120 hrs)

________________________________________________________________________________

### 6.3 Reassignment Trigger Points

#### Trigger Conditions (All must be met):

✅ Mobile apps have completed all core features

✅ Mobile apps are functionally tested and stable

✅ No critical or high-priority mobile bugs remaining

✅ Frontend development is behind schedule or at risk

✅ Mobile developers have completed knowledge transfer

#### Reassignment Decision Points:

Early Reassignment (Feb 7, 2026):

If mobile development is ahead of schedule

Frontend is showing delays

Immediate reassignment of 1 mobile developer

Full Reassignment (Feb 10, 2026):

Mobile MVP complete and tested

Both mobile developers available

Frontend needs maximum support

Partial Reassignment (Flexible):

Keep 0.5 FTE for mobile bug fixes and polish

Assign 1.5 FTE to frontend support

________________________________________________________________________________

### 6.4 Skill Gap Analysis & Training Plan

#### Required Frontend Skills for Mobile Developers

| Skill | Mobile Dev Current Level | Required Level | Training Time | Training Method |
| --- | --- | --- | --- | --- |
| React.js (vs React Native) | Intermediate | Intermediate | 8 hrs | Self-study + pairing |
| Next.js Framework | Beginner | Basic | 16 hrs | Documentation + pairing |
| Tailwind CSS | Intermediate | Intermediate | 4 hrs | Quick review |
| Redux/Context (Web) | Intermediate | Intermediate | 4 hrs | Code review |
| REST API Integration (Web) | Advanced | Advanced | 0 hrs | No training needed |
| Form Handling (Web) | Intermediate | Intermediate | 4 hrs | Examples review |
| Responsive Web Design | Intermediate | Intermediate | 4 hrs | Quick review |
| Component Libraries (Material-UI/Ant Design) | Beginner | Basic | 8 hrs | Documentation review |
| **Total Training Time** | - | - | **48 hrs** | **1 week** |

#### Training Schedule (Week 7: Jan 31 - Feb 6)

Mobile Dev 1 Focus Areas:

Next.js routing and SSR

Component architecture

State management patterns

Day 1-2: Next.js fundamentals (16 hrs)

Day 3: Tailwind CSS & component libraries (12 hrs)

Day 4: Pairing with Frontend Dev (8 hrs)

Day 5-6: Practice on non-critical components (12 hrs)

Mobile Dev 2 Focus Areas:

Form handling & validation

API integration patterns

Complex UI components

Day 1-2: React.js refresher & Next.js basics (16 hrs)

Day 3: Forms & validation (12 hrs)

Day 4: Pairing with Frontend Dev (8 hrs)

Day 5-6: Practice on utility components (12 hrs)

________________________________________________________________________________

### 6.5 Reassignment Allocation Plan

#### Phase 1: Preparation (Jan 31 - Feb 6, 2026)

Week 7 - Training & Knowledge Transfer

| Developer | Time Allocation | Activities |
| --- | --- | --- |
| Mobile Dev 1 | 40% Mobile (32 hrs)<br>60% Training (48 hrs) | - Complete mobile critical features<br>- Frontend training<br>- Pairing sessions |
| Mobile Dev 2 | 40% Mobile (32 hrs)<br>60% Training (48 hrs) | - Complete mobile critical features<br>- Frontend training<br>- Pairing sessions |
| Frontend Dev | 80% Development (64 hrs)<br>20% Training Support (16 hrs) | - Continue frontend work<br>- Mentor mobile devs<br>- Prepare task list |

________________________________________________________________________________

#### Phase 2: Soft Reassignment (Feb 7 - Feb 13, 2026)

Week 8 - Gradual Transition

| Developer | Time Allocation | Primary Tasks |
| --- | --- | --- |
| Mobile Dev 1 | 30% Mobile (24 hrs)<br>70% Frontend (56 hrs) | **Frontend:**<br>- Payment Management UI components<br>- Form components<br>- API integration helpers<br><br>**Mobile:**<br>- Bug fixes<br>- Polish & optimization |
| Mobile Dev 2 | 30% Mobile (24 hrs)<br>70% Frontend (56 hrs) | **Frontend:**<br>- Customer Support UI components<br>- Data tables<br>- Dashboard widgets<br><br>**Mobile:**<br>- Testing support<br>- Documentation |
| Frontend Dev | 100% Frontend (80 hrs) | - Claim Management UI (complex)<br>- State management<br>- Integration orchestration<br>- Code reviews |

Total Frontend Capacity Week 8: 192 hrs (Frontend Dev 80 + Mobile Dev 1 56 + Mobile Dev 2 56)

________________________________________________________________________________

#### Phase 3: Full Reassignment (Feb 14 - Feb 27, 2026)

Weeks 9-10 - Maximum Frontend Support

| Developer | Time Allocation | Primary Tasks |
| --- | --- | --- |
| Mobile Dev 1 | 10% Mobile (8 hrs)<br>90% Frontend (72 hrs) | **Frontend:**<br>- Reports & Analytics UI<br>- Advanced dashboard features<br>- Performance optimization<br>- E2E testing support<br><br>**Mobile:**<br>- Critical bug fixes only |
| Mobile Dev 2 | 10% Mobile (8 hrs)<br>90% Frontend (72 hrs) | **Frontend:**<br>- Notification Center<br>- Settings & Configuration<br>- Responsive design fixes<br>- Integration testing<br><br>**Mobile:**<br>- Critical bug fixes only |
| Frontend Dev | 100% Frontend (80 hrs) | - Complex integrations<br>- Final polish<br>- Performance tuning<br>- Team coordination |

Total Frontend Capacity Weeks 9-10: 224 hrs per week (Frontend Dev 80 + Mobile Dev 1 72 + Mobile Dev 2 72)

________________________________________________________________________________

### 6.6 Task Assignment Strategy

#### Task Complexity Levels for Reassigned Developers

Week 8 (Learning Phase) - Assign Simple Tasks:

✅ Simple form components

✅ Static pages

✅ Utility functions

✅ API integration helpers

✅ CSS styling tasks

❌ Complex state management

❌ Critical path features

❌ Architecture decisions

Weeks 9-10 (Productive Phase) - Assign Medium Tasks:

✅ Complete page components

✅ Dashboard widgets

✅ Data tables with CRUD

✅ Form validation logic

✅ API integrations

✅ E2E testing

⚠️ Complex workflows (with supervision)

❌ Core architecture changes

#### Recommended Task List for Mobile Developers

Mobile Dev 1 - Best Suited For:

Payment Management UI (forms, validation)

Reports & Analytics pages (data visualization)

Settings & Configuration pages

API integration layer improvements

Performance optimization (lazy loading, code splitting)

E2E test scenarios

Mobile Dev 2 - Best Suited For:

Customer Support UI (ticket system, chat)

Notification Center (real-time updates)

Dashboard widgets (charts, cards)

Responsive design fixes

Component library standardization

Integration testing support

________________________________________________________________________________

### 6.7 Coordination & Communication Plan

#### Daily Coordination (During Reassignment Period)

Morning Sync (30 minutes - 9:30 AM):

Participants: Frontend Dev, Mobile Dev 1, Mobile Dev 2, Backend Lead

Purpose: Task assignment, blocker discussion, Q&A

Format: Quick standup + pairing assignments

End-of-Day Review (15 minutes - 5:00 PM):

Participants: Same as morning

Purpose: Progress check, code review scheduling

Format: Quick demo + tomorrow's planning

#### Code Review Process:

All mobile dev frontend code: Must be reviewed by Frontend Dev

Complexity threshold: Medium+ tasks require pairing session

Review SLA: Within 4 hours of PR submission

Merge authority: Frontend Dev has final approval

#### Knowledge Sharing:

Documentation: Frontend Dev maintains component guide

Pairing Sessions: Minimum 2 hours/week per mobile dev

Slack Channel: Dedicated #frontend-support channel

Code Examples: Repository of reusable patterns

________________________________________________________________________________

### 6.8 Risk Management

#### Identified Risks & Mitigation

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| **Mobile developers struggle with Next.js** | High | Medium | - Early training (Week 7)<br>- Start with simple tasks<br>- Daily pairing sessions<br>- Frontend Dev mentorship |
| **Mobile bugs discovered late** | Medium | Low | - Retain 10% capacity for mobile<br>- QA continuous testing<br>- Bug triage process<br>- Escalation to mobile devs if needed |
| **Frontend Dev becomes bottleneck for reviews** | High | High | - Automated code quality checks<br>- Pre-defined component patterns<br>- Backend Lead backup reviewer<br>- Clear review priorities |
| **Quality drops due to rushed work** | High | Medium | - Maintain code review standards<br>- Automated testing<br>- QA early involvement<br>- Buffer time included |
| **Communication overhead increases** | Low | High | - Structured sync meetings<br>- Clear documentation<br>- Dedicated Slack channel<br>- Weekly retrospectives |
| **Mobile devs demotivated by context switching** | Medium | Low | - Clear communication of reasoning<br>- Recognition of flexibility<br>- Return to mobile for M2<br>- Learning opportunity framing |

________________________________________________________________________________

### 6.9 Success Metrics

#### Measuring Reassignment Effectiveness

Productivity Metrics:

Mobile Dev output: Target 70% of Frontend Dev velocity by Week 9

Task completion rate: >90% of assigned tasks completed on time

Code review cycles: Average <2 iterations per PR

Bug introduction rate: <10% increase compared to Frontend Dev baseline

Quality Metrics:

Code quality score: Maintain >80% (using SonarQube/similar)

Test coverage: Maintain >70% for new code

Performance: No regression in page load times

Accessibility: WCAG 2.1 AA compliance

Timeline Metrics:

Frontend completion date: On or before Feb 27, 2026

M1 delivery: On schedule (March 1, 2026)

Buffer utilization: <50% of allocated buffer time used

Team Metrics:

Team satisfaction: >4/5 in sprint retrospectives

Knowledge transfer success: Mobile devs rate themselves >3/5 on frontend skills

Collaboration score: >4/5 cross-team collaboration rating

________________________________________________________________________________

### 6.10 Post-Reassignment Plan

#### Return to Mobile Development (M2 Phase)

Sprint 6 (Mar 2 - Mar 15, 2026):

Mobile developers return to mobile app enhancements

Implement M2 mobile features:

Offline mode improvements

Advanced notifications

Performance optimization

Additional agent app features

Knowledge Retention:

Mobile developers can still support frontend during M2/M3 if needed

Cross-functional capability adds team flexibility

Future features can be distributed more evenly

Skill Development:

Mobile developers gain full-stack experience

Frontend developer learns mobile considerations

Team becomes more versatile and resilient

________________________________________________________________________________

### 6.11 Alternative Scenarios

#### Scenario A: Mobile Development Delayed

If mobile MVP not ready by Feb 10:

Reassess mobile timeline and blockers

Delay reassignment to Feb 17 if needed

Increase Frontend Dev hours (evenings/weekends) if critical

Consider reducing frontend scope for M1

#### Scenario B: Frontend Development Ahead of Schedule

If frontend on track by Feb 10:

Reassign only 1 mobile developer (50% capacity)

Use second mobile dev for:

Advanced mobile features

Mobile testing & polish

API testing support

Backend integration testing

#### Scenario C: Critical Mobile Bug Post-Reassignment

If major mobile issue discovered:

Immediately pull back 1 mobile developer

Other mobile dev continues frontend support at reduced capacity

QA prioritizes mobile regression testing

Consider hotfix release if critical

________________________________________________________________________________

### 6.12 Reassignment Decision Framework

#### Weekly Reassignment Review Checklist

Week 7 Review (Feb 6, 2026):

[ ] Mobile MVP features 90%+ complete

[ ] Mobile critical bugs count < 5

[ ] Mobile dev training completion > 80%

[ ] Frontend delay risk > 50%

[ ] Decision: Proceed with Week 8 soft reassignment

Week 8 Review (Feb 13, 2026):

[ ] Mobile MVP fully tested and stable

[ ] Mobile devs productive in frontend (>50% velocity)

[ ] Frontend still needs support

[ ] No critical mobile escalations

[ ] Decision: Proceed with full reassignment

Week 9 Review (Feb 20, 2026):

[ ] Frontend on track for Feb 27 completion

[ ] Mobile devs fully productive (>70% velocity)

[ ] Quality metrics maintained

[ ] Team morale positive

[ ] Decision: Continue until M1 complete

________________________________________________________________________________

### 6.13 Communication Templates

#### Announcement Email (Sent Feb 1, 2026)

Subject: Mobile Team Reassignment Plan - Supporting M1 Success

Dear Team,

Great news! Our mobile development team has made excellent progress and is 
ahead of schedule. To ensure we deliver a stellar M1 release, we'll be 
implementing a strategic reassignment plan:

Timeline:
- Week 7 (Jan 31 - Feb 6): Mobile devs begin frontend training
- Week 8 (Feb 7 - Feb 13): Gradual transition (70% frontend)
- Weeks 9-10 (Feb 14 - Feb 27): Full support (90% frontend)

This demonstrates our team's flexibility and commitment to project success.
Mobile developers will return to mobile enhancements in M2.

Benefits:
✅ Accelerated frontend development
✅ Reduced single-point-of-failure risk
✅ Cross-functional skill development
✅ On-time M1 delivery

We'll have daily syncs and strong mentorship support. Thank you for your
adaptability and teamwork!

Best regards,
Project Management

________________________________________________________________________________

### 6.14 Summary & Recommendations

#### Key Recommendations:

Start Training Early: Begin frontend training in Week 7 (Jan 31)

Gradual Transition: Don't abruptly switch; use Week 8 for soft transition

Maintain Quality: Don't sacrifice code quality for speed

Strong Mentorship: Frontend Dev must be available for guidance

Daily Coordination: 30-minute daily syncs are critical

Keep Mobile Buffer: Retain 10% capacity for mobile issues

Measure Success: Track productivity and quality metrics

Clear Communication: Transparent about reasons and expectations

Celebrate Flexibility: Recognize team adaptability

Plan Return: Clear path back to mobile work in M2

#### Expected Outcomes:

With Reassignment:

Frontend completion: Feb 27, 2026 ✅ On time

M1 delivery: March 1, 2026 ✅ On time

Team utilization: 85%+ ✅ High

Risk level: Low ✅ Manageable

Without Reassignment:

Frontend completion: March 5-7, 2026 ⚠️ Late

M1 delivery: March 8-10, 2026 ❌ Delayed

Team utilization: Frontend 100%, Mobile 30% ⚠️ Imbalanced

Risk level: High ❌ Single point of failure

Recommendation: Proceed with reassignment strategy as planned.

________________________________________________________________________________

________________________________________________________________________________

## 7. Risks and Mitigation Strategies

### 7.1 Risk Assessment Framework

Risk Scoring:

Probability: Low (1), Medium (2), High (3)

Impact: Low (1), Medium (2), High (3), Critical (4)

Risk Score: Probability × Impact

Priority: Critical (9-12), High (6-8), Medium (3-5), Low (1-2)

________________________________________________________________________________

### 7.2 Technical Risks

#### Risk T1: Backend Service Integration Complexity

Category: Technical | Priority: HIGH (Score: 9)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | High (3) |
| **Description** | Multiple microservices need to communicate seamlessly. Integration issues could cause cascading delays. |
| **Triggers** | - API contract mismatches<br>- Data format inconsistencies<br>- Synchronous dependencies<br>- Network latency issues |
| **Impact Areas** | - M1 timeline at risk<br>- Testing delays<br>- Bug multiplication<br>- Team productivity loss |

Mitigation Strategies:

✅ Contract-First Development: Define API contracts (OpenAPI/Swagger) before implementation

✅ Early Integration Testing: Start integration tests from Sprint 2

✅ Service Mocking: Use mock services for parallel development

✅ API Gateway: Centralized API management with versioning

✅ Weekly Integration Reviews: Dedicated sessions to identify issues early

✅ Event-Driven Architecture: Use message queues for loose coupling

Contingency Plan:

Dedicated integration sprint if issues persist

Escalate to architecture review board

Consider synchronous fallbacks for critical paths

________________________________________________________________________________

#### Risk T2: Database Performance Bottlenecks

Category: Technical | Priority: HIGH (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | Poor database design or inefficient queries could cause performance issues. |
| **Triggers** | - Missing indexes<br>- N+1 query problems<br>- Large data volumes<br>- Concurrent access issues |

Mitigation Strategies:

✅ Database Design Review: Expert review of schema design in Sprint 1

✅ Query Optimization: Use query analyzers and explain plans

✅ Indexing Strategy: Proper indexes on frequently queried columns

✅ Caching Layer: Redis/Memcached for frequently accessed data

✅ Load Testing: Regular performance testing from Sprint 3

✅ Database Monitoring: Real-time monitoring of query performance

________________________________________________________________________________

#### Risk T3: Third-Party Service Dependencies

Category: Technical | Priority: MEDIUM (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | Payment gateways, SMS providers, cloud storage could fail or have downtime. |
| **Triggers** | - Service outages<br>- API changes<br>- Rate limiting<br>- Authentication issues |

Mitigation Strategies:

✅ Fallback Providers: Secondary providers for critical services

✅ Circuit Breakers: Implement circuit breaker pattern

✅ Graceful Degradation: System continues with reduced functionality

✅ Retry Mechanisms: Exponential backoff for transient failures

✅ Monitoring & Alerts: Real-time monitoring of third-party services

✅ SLA Review: Understand provider SLAs and support options

________________________________________________________________________________

#### Risk T4: Security Vulnerabilities

Category: Security | Priority: CRITICAL (Score: 12)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | Critical (4) |
| **Description** | Security breaches could expose sensitive insurance and personal data. |
| **Triggers** | - SQL injection<br>- XSS attacks<br>- Authentication bypass<br>- Data exposure<br>- API vulnerabilities |

Mitigation Strategies:

✅ Security Reviews: Code reviews focused on security from Sprint 1

✅ OWASP Guidelines: Follow OWASP Top 10 best practices

✅ Penetration Testing: Professional security audit before M1

✅ Input Validation: Strict validation on all user inputs

✅ Encryption: Data encryption at rest and in transit (TLS/SSL)

✅ Security Tools: SonarQube, Snyk for vulnerability scanning

✅ Access Control: Proper RBAC implementation and testing

✅ Audit Logging: Comprehensive logging of sensitive operations

________________________________________________________________________________

#### Risk T5: Frontend Single Point of Failure

Category: Resource | Priority: HIGH (Score: 8)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | Medium-High (2.5) |
| **Description** | Only one frontend developer; if unavailable, frontend work stops completely. |
| **Triggers** | - Developer illness<br>- Personal emergency<br>- Resignation<br>- Burnout |

Mitigation Strategies:

✅ Mobile Dev Reassignment: Planned reassignment from Week 8

✅ Knowledge Sharing: Documentation and code reviews

✅ Component Library: Reusable components reduce complexity

✅ Backup Developer: Backend Lead has frontend experience (limited)

✅ Early Start: Frontend work begins Sprint 1, not later

✅ Workload Management: Monitor workload and prevent burnout

Contingency Plan:

Immediate mobile developer activation

Reduce frontend scope if necessary

Consider temporary contractor if long-term unavailability

________________________________________________________________________________

### 7.3 Schedule Risks

#### Risk S1: Aggressive M1 Timeline

Category: Schedule | Priority: CRITICAL (Score: 12)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | Critical (4) |
| **Description** | 60 working days to deliver 7,483 hours of work is extremely tight. |
| **Triggers** | - Underestimated complexity<br>- Unexpected technical challenges<br>- Scope creep<br>- Resource unavailability |

Mitigation Strategies:

✅ Parallel Development: All teams work simultaneously

✅ Priority Management: Strict adherence to M1 scope, defer non-critical features

✅ Buffer Time: Built-in 2-day buffer before M1

✅ Mobile Reassignment: Add 240 hours to frontend from Week 8

✅ Daily Tracking: Monitor progress daily, not weekly

✅ Early Warnings: Raise flags at first sign of delay

✅ Scope Flexibility: Ready to cut "nice-to-have" features

Contingency Plan:

Reduce mobile features to absolute minimum

Defer advanced features to M1.1 patch release

Add overtime (limited, sustainable)

Escalate to stakeholders for scope/timeline negotiation

________________________________________________________________________________

#### Risk S2: Holiday Impact During Critical Period

Category: Schedule | Priority: MEDIUM (Score: 4)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) - Already known |
| **Impact** | Low-Medium (1.5) |
| **Description** | Two holidays (Feb 4, Feb 21) during Sprint 4-5 reduce available working days. |
| **Triggers** | - Public holidays<br>- Reduced productivity around holidays |

Mitigation Strategies:

✅ Already Excluded: Holidays removed from working day calculations

✅ Sprint Planning: Sprints 4-5 planned with reduced capacity

✅ Pre-Holiday Push: Complete critical work before holidays

✅ Post-Holiday Recovery: Plan lighter work immediately after

Note: Already mitigated in planning; minimal residual risk.

________________________________________________________________________________

#### Risk S3: Testing Phase Delays

Category: Schedule | Priority: HIGH (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | If testing is pushed to the end, bugs could delay M1 delivery. |
| **Triggers** | - Late development completion<br>- High bug count<br>- Complex integration issues<br>- Inadequate test coverage |

Mitigation Strategies:

✅ Continuous Testing: QA testing starts from Sprint 2

✅ Test Automation: Automated tests run on every commit

✅ Shift-Left Testing: Developers write unit tests during development

✅ Weekly QA Reviews: QA reports progress and blockers weekly

✅ Bug Triage: Daily bug triage in Sprints 4-5

✅ Acceptance Criteria: Clear DoD with testing requirements

________________________________________________________________________________

### 7.4 Resource Risks

#### Risk R1: Team Member Unavailability

Category: Resource | Priority: HIGH (Score: 8)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | Critical (4) |
| **Description** | Key team members could be unavailable due to illness, emergency, or resignation. |
| **Triggers** | - Illness<br>- Family emergency<br>- Resignation<br>- Accident |

Mitigation Strategies:

✅ Knowledge Sharing: Documentation and pair programming

✅ Code Reviews: Multiple people understand each codebase

✅ Cross-Training: Mobile devs learn frontend, etc.

✅ Backup Contacts: Identify backup for each critical role

✅ Documentation: Comprehensive technical documentation

✅ Onboarding Ready: Have contractor onboarding process ready

Contingency Plan:

Activate cross-trained team members

Bring in contractor (2-3 day lead time)

Redistribute work among remaining team

Escalate to stakeholders if critical role unavailable >5 days

________________________________________________________________________________

#### Risk R2: Skill Gaps in Team

Category: Resource | Priority: MEDIUM (Score: 4)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | Medium (2) |
| **Description** | Team may lack specific technical skills (e.g., payment gateway integration, Kubernetes). |
| **Triggers** | - First-time technology use<br>- Complex feature requirements<br>- Vendor-specific knowledge needed |

Mitigation Strategies:

✅ Training Time: Allocate learning time in capacity planning

✅ Expert Consultation: Budget for external consultants if needed

✅ Vendor Support: Utilize vendor technical support

✅ Proof of Concepts: Try risky technologies early (Sprint 1-2)

✅ Pair Programming: Learn from each other

✅ Documentation Review: Study official documentation thoroughly

________________________________________________________________________________

#### Risk R3: Team Burnout

Category: Resource | Priority: HIGH (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | Aggressive timeline could lead to team exhaustion and reduced productivity. |
| **Triggers** | - Long hours<br>- Weekend work<br>- High pressure<br>- Lack of breaks<br>- Unclear priorities |

Mitigation Strategies:

✅ Realistic Planning: Buffer built into estimates

✅ Work-Life Balance: Discourage excessive overtime

✅ Clear Priorities: Focus on what matters, cut low-priority items

✅ Sprint Retrospectives: Address team concerns regularly

✅ Celebration: Recognize achievements and milestones

✅ Mental Health: Encourage breaks and time off

✅ Workload Monitoring: Track hours and adjust if needed

Warning Signs:

Increased sick days

Missed deadlines

Quality decline

Low team morale

Conflict increase

________________________________________________________________________________

### 7.5 Scope Risks

#### Risk SC1: Scope Creep

Category: Scope | Priority: HIGH (Score: 8)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | Medium-High (2.5) |
| **Description** | Stakeholders or team add features beyond M1 scope during development. |
| **Triggers** | - Stakeholder requests<br>- "Quick features"<br>- Gold plating<br>- Market changes<br>- Competitor features |

Mitigation Strategies:

✅ Change Control Process: Formal process for scope changes

✅ Priority Framework: M1/M2/M3 clearly defined

✅ Product Owner Authority: PO has final say on scope

✅ Impact Assessment: Every change request analyzed for impact

✅ Backlog for Later: New ideas go to M2/M3 backlog

✅ Stakeholder Education: Explain timeline implications

Change Control Process:

Request submitted to Product Owner

Impact analysis (effort, timeline, dependencies)

Present to stakeholders with trade-offs

Decision: Approve & adjust timeline, defer to M2/M3, or reject

Update project plan if approved

________________________________________________________________________________

#### Risk SC2: Requirement Ambiguity

Category: Scope | Priority: MEDIUM (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | Unclear or changing requirements lead to rework and delays. |
| **Triggers** | - Vague specifications<br>- Assumptions made<br>- Stakeholder disagreement<br>- Missing edge cases |

Mitigation Strategies:

✅ Detailed SRS: Comprehensive SRS document (v3.7)

✅ User Stories: Clear acceptance criteria for each story

✅ Mockups/Prototypes: Visual validation before coding

✅ Backlog Refinement: Weekly sessions to clarify requirements

✅ Sprint Reviews: Regular stakeholder feedback

✅ Question Log: Document and resolve ambiguities quickly

________________________________________________________________________________

### 7.6 Quality Risks

#### Risk Q1: Insufficient Testing Coverage

Category: Quality | Priority: HIGH (Score: 9)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | High (3) |
| **Description** | Rushing development could result in inadequate testing and poor quality. |
| **Triggers** | - Time pressure<br>- Late testing start<br>- Complex integration<br>- Lack of automation |

Mitigation Strategies:

✅ Test Early: QA involvement from Sprint 1

✅ Definition of Done: Testing required before marking complete

✅ Automation: Automated unit, integration, and E2E tests

✅ Code Coverage: Target >70% code coverage

✅ Test Environments: Dedicated dev, staging, UAT environments

✅ QA Resources: 2 dedicated QA testers

✅ Regression Suite: Automated regression tests

________________________________________________________________________________

#### Risk Q2: Technical Debt Accumulation

Category: Quality | Priority: MEDIUM (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | High (3) |
| **Impact** | Medium (2) |
| **Description** | Quick fixes and shortcuts now create maintenance burden later. |
| **Triggers** | - Time pressure<br>- Lack of refactoring<br>- Skipped code reviews<br>- Poor documentation |

Mitigation Strategies:

✅ Code Reviews: Mandatory reviews for all code

✅ Refactoring Time: Allocate time in each sprint for refactoring

✅ Technical Debt Log: Track debt and plan paydown

✅ Code Quality Tools: SonarQube for quality metrics

✅ Architecture Reviews: Regular reviews to prevent architectural debt

✅ Documentation: Maintain up-to-date documentation

Acceptable Debt:

M1 may accept some debt if trade-off is clear

Must be documented and planned for M2/M3

Critical systems should have minimal debt

________________________________________________________________________________

### 7.7 External Risks

#### Risk E1: Stakeholder Changes or Delays

Category: External | Priority: MEDIUM (Score: 6)

| Attribute | Details |
| --- | --- |
| **Probability** | Medium (2) |
| **Impact** | High (3) |
| **Description** | Stakeholder decisions, approvals, or feedback could be delayed. |
| **Triggers** | - Slow approval process<br>- Stakeholder unavailability<br>- Changing priorities<br>- Budget issues |

Mitigation Strategies:

✅ Clear Communication: Regular stakeholder updates

✅ Early Involvement: Involve stakeholders from Sprint 1

✅ Decision Log: Document all decisions with dates

✅ Escalation Path: Clear escalation for blocked decisions

✅ Autonomous Work: Design system allows parallel work without approvals

✅ Sprint Reviews: Regular demos to maintain engagement

________________________________________________________________________________

#### Risk E2: Regulatory or Compliance Changes

Category: External | Priority: LOW (Score: 2)

| Attribute | Details |
| --- | --- |
| **Probability** | Low (1) |
| **Impact** | Medium (2) |
| **Description** | Insurance regulations or data privacy laws could change during development. |
| **Triggers** | - New laws<br>- Regulatory updates<br>- Industry standards<br>- Government mandates |

Mitigation Strategies:

✅ Compliance Awareness: Monitor regulatory updates

✅ Flexible Design: Modular architecture allows quick changes

✅ Legal Review: Periodic compliance reviews

✅ Industry Best Practices: Follow established standards

________________________________________________________________________________

### 7.8 Risk Register Summary

| Risk ID | Risk Name | Category | Probability | Impact | Score | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| T4 | Security Vulnerabilities | Security | High | Critical | 12 | CRITICAL |
| S1 | Aggressive M1 Timeline | Schedule | High | Critical | 12 | CRITICAL |
| T1 | Backend Integration Complexity | Technical | High | High | 9 | HIGH |
| Q1 | Insufficient Testing | Quality | High | High | 9 | HIGH |
| R1 | Team Member Unavailability | Resource | Medium | Critical | 8 | HIGH |
| T5 | Frontend Single Point of Failure | Resource | High | Medium | 8 | HIGH |
| SC1 | Scope Creep | Scope | High | Medium | 8 | HIGH |
| T2 | Database Performance | Technical | Medium | High | 6 | HIGH |
| T3 | Third-Party Dependencies | Technical | Medium | High | 6 | HIGH |
| S3 | Testing Phase Delays | Schedule | Medium | High | 6 | HIGH |
| R3 | Team Burnout | Resource | Medium | High | 6 | HIGH |
| SC2 | Requirement Ambiguity | Scope | Medium | High | 6 | HIGH |
| Q2 | Technical Debt | Quality | High | Medium | 6 | MEDIUM |
| E1 | Stakeholder Delays | External | Medium | High | 6 | MEDIUM |
| S2 | Holiday Impact | Schedule | High | Low | 4 | MEDIUM |
| R2 | Skill Gaps | Resource | Medium | Medium | 4 | MEDIUM |
| E2 | Regulatory Changes | External | Low | Medium | 2 | LOW |

________________________________________________________________________________

### 7.9 Risk Monitoring and Review

#### Weekly Risk Review (Every Friday)

Participants: Project Manager, Team Leads

Duration: 30 minutes

Agenda:

Review risk register

Assess new risks

Update risk status

Review mitigation effectiveness

Plan actions for next week

#### Risk Escalation Criteria:

Immediate Escalation: Critical risks (score 9-12) materialize

Weekly Report: High risks (score 6-8) status

Monthly Review: All risks with stakeholders

#### Risk Ownership:

Project Manager: Overall risk management

Backend Lead: Technical risks

QA Lead: Quality risks

Product Owner: Scope and stakeholder risks

DevOps: Infrastructure and security risks

________________________________________________________________________________

### 7.10 Risk Response Strategies

#### Four Response Types:

1. Avoid:

Eliminate the risk by changing approach

Example: Use proven technology instead of experimental one

2. Mitigate:

Reduce probability or impact

Example: Add buffer time, cross-train team members

3. Transfer:

Shift risk to third party

Example: Use managed services, insurance

4. Accept:

Acknowledge risk and prepare contingency

Example: Some technical debt acceptable for M1

________________________________________________________________________________

________________________________________________________________________________

# Requirements Distribution by Milestone

## Overview

Total Requirements in SRS V3.7: 345 functional requirements

| Priority | Count | Percentage | Target Milestone |
| --- | --- | --- | --- |
| **M1** | 103 | 29.9% | Beta Launch - March 1, 2026 |
| **M2** | 92 | 26.7% | Grand Launch - April 14, 2026 |
| **M3** | 81 | 23.5% | Complete Platform - August 1, 2026 |
| **D (Desirable)** | 53 | 15.4% | Post M3 / Future phases |
| **S (Should Have)** | 1 | 0.3% | As needed |
| **F (Future)** | 15 | 4.3% | Future releases |

________________________________________________________________________________

## M1 - Beta Launch (March 1, 2026) - 103 Requirements

### Strategy: **Barebone Functional Platform**

Goal: Prove the concept with minimal viable features

Target Users: Early adopters, limited partner base (2-3 partners)

Scope: End-to-end flow for 1 insurance product type

### M1 Core Features (Implemented)

#### Authentication & Authorization (FG-001, FG-002) - 16 Requirements

| FR ID | Requirement | Implementation Notes |
| --- | --- | --- |
| FR-001 to FR-009 | Core authentication (mobile, email, password, OTP, session) | ✅ Using CTO's existing Go services (100% ready) |
| FR-014 to FR-018 | RBAC, ABAC, ACL | ✅ Using CTO's existing Authorization service |

Effort Saved: ~500 hours (existing code reuse)

________________________________________________________________________________

#### Product & Policy Management (FG-003, FG-004) - 20 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-021, FR-022 | Product catalog with search | Single product category (Health) |
| FR-026 | Product CRUD by Business Admin | Basic operations only |
| FR-030 to FR-034 | End-to-end policy purchase flow | Simplified flow, single nominee |
| FR-039, FR-040 | Policy status tracking and dashboard | Basic statuses only |
| FR-091, FR-092 | Policy document and lifecycle tracking | PDF generation, basic audit |

Services Required:

Insurance Engine (C# .NET) - Mr. Delowar's team - 748 hrs

Basic product catalog (10 products max)

________________________________________________________________________________

#### Claims Management (FG-008) - **MOVED TO M2**

| FR ID | Requirement | Scope for M2 |
| --- | --- | --- |
| FR-041 to FR-043 | Claim submission and validation | Full workflow with approval |
| FR-044 to FR-058 | Claim tracking, approval, fraud detection | Complete claims system |
| FR-218 to FR-219 | Claim status state machine | Full state machine |

Services Required (M2):

Claim Service (C# .NET) - 634 hrs (full implementation)

Tiered approval workflow with Business Admin + Focal Person

Fraud detection and document verification

M1 Decision: Claims REMOVED from M1 scope due to capacity constraints. M1 focuses on policy purchase demo only. Claims processing begins M2 (April 14, 2026).

________________________________________________________________________________

#### Payment Processing (FG-007) - 8 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-073, FR-074 | bKash payment gateway | ✅ Mamoon's existing code (70% ready) |
| FR-076, FR-077 | Manual payment with verification | Basic workflow |
| FR-083 | Payment audit trail | PostgreSQL logging |

Effort Saved: ~357 hours (Mamoon's existing payment service)

________________________________________________________________________________

#### Document Management (FG-005) - 6 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-232, FR-237 | File upload and S3 storage | ✅ CTO's Storage Manager (100% ready) |
| FR-239 | Upload policies and compression | Client-side validation |

Effort Saved: ~333 hours (CTO's existing Storage Manager)

________________________________________________________________________________

#### Notifications (FG-012) - 8 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-114, FR-115 | Kafka-based notifications (SMS, email, push) | Basic templates only |
| FR-161, FR-162 | SMS and email integration | Essential notifications only |

Services Required:

Notification Service (Go + Kafka) - CTO - 431 hrs

________________________________________________________________________________

#### Partner Management (FG-009) - 10 Requirements (REDUCED SCOPE)

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-066 | Focal Person portal for partner management | ⚠️ **DEFERRED to M2** |
| FR-192 | RACI for monitoring and escalation | Manual process in M1 |

M1 Decision: Manual partner onboarding, no automated portal

________________________________________________________________________________

#### Customer Support (FG-011) - 6 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-106 | FAQ section with searchable knowledge base | Static FAQ page |
| FR-108, FR-109 | Ticketing system | Basic support ticketing |

Services Required:

Ticketing Service (Node.js) - Mamoon + Sujon - 352 hrs

________________________________________________________________________________

#### Admin & Reporting (FG-017) - 8 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-131, FR-132 | Admin dashboards with 2FA | System Admin + Partner portal only |
| FR-134, FR-135 | Product and claims management | Basic CRUD operations |
| FR-140 | System health monitoring | Basic Prometheus/Grafana |

________________________________________________________________________________

#### Audit & Logging (FG-019) - 5 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| FR-153, FR-154 | Immutable audit logs with 20-year retention | PostgreSQL + S3 archival |
| FR-083 | Payment audit trail | Integrated with payment service |

________________________________________________________________________________

#### Security & Compliance (SEC) - 4 Requirements

| FR ID | Requirement | Scope for M1 |
| --- | --- | --- |
| SEC-001, SEC-002 | Zero Trust architecture, encryption at rest/transit | TLS 1.3, AES-256 |
| SEC-003 | PCI-DSS SAQ-A compliance for payments | bKash hosted payment page |
| FR-192 | RACI for monitoring | Basic monitoring setup |

________________________________________________________________________________

### M1 Web Portals - **2 PORTALS ONLY (ALIGNED WITH 04_EffortEstimation.md)**

DECISION: Business Admin + Partner portals for M1 (matches 04_EffortEstimation.md line 233-256)

#### Portal 1: Business Admin Portal (Priority 1)

Purpose: Business managers manage products, policies, and core operations

| Feature | Complexity | Hours |
| --- | --- | --- |
| Design System Setup (Tailwind/Shadcn) | Medium | 40 hrs |
| Authentication UI (Shared) | Low | 24 hrs |
| Navigation & Layout System | Medium | 32 hrs |
| State Management (Redux/Zustand) | Medium | 24 hrs |
| API Integration Layer | Medium | 32 hrs |
| Business Admin Portal (Product/Policy CRUD) | High | 72 hrs |
| Notification Center (Basic) | Low | 16 hrs |
| Responsive Design | Medium | 24 hrs |
| Error Handling & Validation | Low | 16 hrs |
| Testing (Unit + E2E) | - | 32 hrs |
| **SUBTOTAL** | - | **312 hrs** |
| **Buffer (10%)** | - | **31 hrs** |
| **TOTAL** | - | **343 hrs** |

________________________________________________________________________________

#### Portal 2: Partner Portal (Priority 2)

Purpose: Insurance partners track leads, commissions, and performance

| Feature | Complexity | Hours |
| --- | --- | --- |
| Partner Portal Dashboard | Medium | 48 hrs |
| Partner Profile Management | Low | 24 hrs |
| Performance Analytics (Basic) | Medium | 32 hrs |
| Commission Tracking | Low | 16 hrs |
| Testing | - | 12 hrs |
| **SUBTOTAL** | - | **132 hrs** |
| **Buffer (10%)** | - | **0 hrs** (included) |
| **TOTAL** | - | **132 hrs** |

________________________________________________________________________________

#### **DEFERRED TO M2:**

❌ System Admin Portal (moved to M2)

❌ Agent Portal (moved to M2)

❌ Customer Support Portal (moved to M2)

#### **DEFERRED TO M3:**

❌ Focal Person Portal (SRS says M1, but capacity insufficient - manual process for M1)

❌ DevOps Portal

❌ Database Manager Portal

❌ 5 other portals

Total M1 Portal Hours: 475 hrs (343 + 132)

Aligned with 04_EffortEstimation.md: ✅ YES

________________________________________________________________________________

### M1 Mobile Apps - **BASIC FEATURES ONLY**

#### Customer App (Android + iOS)

| Feature | Android | iOS | Total |
| --- | --- | --- | --- |
| Authentication | 20 hrs | 20 hrs | 40 hrs |
| Dashboard (policy list) | 24 hrs | 24 hrs | 48 hrs |
| Policy Purchase Flow | 40 hrs | 40 hrs | 80 hrs |
| Policy Details View | 24 hrs | 24 hrs | 48 hrs |
| Claim Filing (basic) | 40 hrs | 40 hrs | 80 hrs |
| Payment (bKash) | 32 hrs | 32 hrs | 64 hrs |
| Document Upload | 24 hrs | 24 hrs | 48 hrs |
| Push Notifications | 16 hrs | 16 hrs | 32 hrs |
| **SUBTOTAL** | **220 hrs** | **220 hrs** | **440 hrs** |
| **Buffer (10%)** | **22 hrs** | **22 hrs** | **44 hrs** |
| **TOTAL** | **242 hrs** | **242 hrs** | **484 hrs** |

________________________________________________________________________________

#### Agent App (Android + iOS) - **DEFERRED TO M2**

Agent dashboard, customer management, lead tracking moved to M2

Agents can use Partner Portal on tablets for M1

Total M1 Mobile Hours: 484 hrs (down from 1,162 hrs)

Savings: 678 hours moved to M2

________________________________________________________________________________

### M1 Infrastructure & DevOps - **ESSENTIAL ONLY**

| Component | Hours | Notes |
| --- | --- | --- |
| Cloud Infrastructure (AWS/Azure) | 32 hrs | Reuse CTO's patterns |
| Docker Containerization | 20 hrs | Basic setup |
| Kubernetes Setup | 48 hrs | Simple cluster |
| CI/CD Pipeline | 40 hrs | GitHub Actions |
| Database Setup (PostgreSQL) | 24 hrs | Single primary |
| Kafka Setup | 32 hrs | For notifications |
| API Gateway Deployment | 24 hrs | 50% existing code |
| Monitoring (Prometheus/Grafana) | 40 hrs | Basic dashboards |
| Security (SSL, WAF) | 32 hrs | Cloudflare |
| Backup & DR | 24 hrs | Daily backups |
| **SUBTOTAL** | **316 hrs** |  |
| **Buffer (10%)** | **32 hrs** |  |
| **TOTAL** | **348 hrs** | Down from 493 hrs |

Savings: 145 hours (reduced complexity)

________________________________________________________________________________

### M1 Effort Summary - FINAL ALIGNED

| Component | Hours | Team | Notes |
| --- | --- | --- | --- |
| User Service (Auth/AuthZ) | 44 hrs | CTO (50%) | ✅ 100% ready |
| Policy Service (Core) | 317 hrs | Delowar + C# Dev (90%) | New C# service |
| Payment Service | 106 hrs | Mamoon (40%) | 70% ready (Bkash) |
| Document Service | 66 hrs | CTO (50%) + Sagor | ✅ 100% ready |
| Notification Service | 176 hrs | CTO (50%) | 80% ready (IoT Broker) |
| Mock Server | 40 hrs | Sujon Ahmed (60%) | For parallel development |
| Business Admin Portal | 343 hrs | React Dev (70%) | With mocks |
| Partner Portal | 132 hrs | React Dev (70%) | With mocks |
| Customer Mobile App (Android) | 317 hrs | Nur Hossain (90%) | With mocks |
| Customer Mobile App (iOS) | 317 hrs | Sojol Ahmed (90%) | With mocks |
| DevOps & Infrastructure | 229 hrs | Sagor (50%) | Basic setup |
| QA & Testing | 414 hrs | 1 QA (60%) | Critical paths with mocks |
| UI/UX Design | 239 hrs | Rumon (60%) | Business Admin + Partner + Mobile |
| **TOTAL M1** | **2,740 hrs** | - | **✅ Matches capacity** |

M1 Available Capacity: 4,040 hours (corrected: +48 hrs from Delowar fix)

M1 Required Effort: 2,740 hours

Utilization: 68% ✅ COMFORTABLE

❌ REMOVED FROM M1:

Claims Service → M2 (634 hrs)

Ticketing Service → M2 (352 hrs)

10 Other Portals → M3 (800 hrs)

Agent Mobile Apps → NOT IN SCOPE (per SRS, agents use web portal)

________________________________________________________________________________

## M2 - Grand Launch (April 14, 2026) - 92 Requirements

### Strategy: **Partner Onboarding & Business Operations**

Goal: Scale to 10-15 partners, add business intelligence

Target: Full partner ecosystem, agent network activated

### M2 Additional Features

#### Partner Portal Enhancements (M2)

Partner onboarding workflow (FR-059 to FR-062)

KYB verification integration

Commission calculation engine

Partner analytics dashboard

API integration for embedded insurance (FR-064)

Effort: 320 hrs

________________________________________________________________________________

#### New Portals (M2)

Portal 3: Business Admin Portal - 280 hrs

Business operations dashboard

Policy approvals and overrides

Financial reconciliation

KPI tracking

Executive reports

Portal 4: Agent Portal - 240 hrs

Agent dashboard

Customer management

Lead tracking

Commission tracking

Mobile-optimized

Total M2 Portal Hours: 520 hrs

________________________________________________________________________________

#### Agent Mobile Apps (M2)

Agent App (Android + iOS) - 420 hrs

Agent dashboard

Customer onboarding

Policy management

Lead tracking

Commission view

________________________________________________________________________________

#### Enhanced Features (M2)

Analytics & Reporting Service (C#) - 440 hrs

Business intelligence dashboards

Predictive analytics

Customer segmentation

Geographic analytics (FR-152, FR-202)

Commission Service (C#) - 324 hrs

Multi-level commission calculation

Agent hierarchy management

Commission payout processing

Performance tracking

Integration Service (C#) - 364 hrs

Third-party API framework

Insurer integrations

EHR/Hospital integrations (FR-229, FR-230)

Webhook management

________________________________________________________________________________

### M2 Effort Summary - FINAL ALIGNED

| Component | Hours | Team | Notes |
| --- | --- | --- | --- |
| Claims Service (Full) | 634 hrs | Delowar + C# Dev (90%) | New backend service |
| Customer Mobile Real API Integration | 320 hrs | Nur + Sojol (90%) | Connect to real APIs |
| Frontend Real API Integration | 200 hrs | React Dev (70%) | Business Admin + Partner |
| Push Notifications | 80 hrs | CTO (50%) + Mobile devs | FCM production |
| Commission tracking | 120 hrs | Mamoon (40%) + Sujon (60%) | Partner feature |
| End-to-End Testing | 200 hrs | 1 QA (60%) | Full integration |
| Bug Fixes & Polish | 87 hrs | All teams | Final touches |
| **TOTAL M2** | **1,641 hrs** | - | **✅ Matches exactly** |

M2 Available Capacity: 2,256 hours (5 weeks × 14 team members)

M2 Required Effort: 1,641 hours

Status: ✅ 73% utilization - COMFORTABLE

Note: M2 focuses on Real API integration for Customer Mobile App + Claims backend + Push Notifications.

________________________________________________________________________________

## M3 - Complete Platform (August 1, 2026) - 81 Requirements

### Strategy: **IoT, AI, and Advanced Features**

Goal: Complete platform with all advanced capabilities

Focus: IoT devices, AI agents, remaining portals, advanced analytics

### M3 Major Features

#### IoT Integration & UBI (FG-013) - **8 M3 + 5 Future + 1 Desirable = 14 IoT Requirements**

IoT Infrastructure (Go) - CTO + Sagor

| Feature | Hours | Notes |
| --- | --- | --- |
| IoT Device Registration & Provisioning (FR-179) | 80 hrs | X.509 certificates, device lifecycle |
| MQTT Broker Setup (FR-180) | 120 hrs | Handle 10,000 devices, TimescaleDB |
| IoT Telemetry Processing (FR-184) | 96 hrs | Kafka Streams, batch/real-time |
| Device Management Portal (FR-183) | 80 hrs | Real-time monitoring, device health |
| Real-time Alerts (FR-181) | 64 hrs | Rule engine, threshold monitoring |
| Usage-Based Insurance Pricing (FR-182) | 120 hrs | Dynamic premium algorithm, scoring |
| Device Inventory (FR-185) | 48 hrs | Registry, heartbeat monitoring |
| IoT Data Dashboard (FR-127) | 80 hrs | Customer-facing insights |
| **SUBTOTAL** | **688 hrs** |  |
| **Buffer (10%)** | **69 hrs** |  |
| **TOTAL IoT** | **757 hrs** |  |

________________________________________________________________________________

#### AI Engine & Multi-Agent Network (FG-014) - **Python Devs (50% time each)**

AI Services Architecture:

Agent 1: Document Processing (OCR, NID validation)

Agent 2: Customer Service (Bengali NLP, chatbot)

Agent 3: Risk Assessment (Fraud detection, claim scoring)

Agent 4: Business Intelligence (Predictive analytics)

| Feature | Hours | Notes |
| --- | --- | --- |
| AI Infrastructure Setup | 80 hrs | Python FastAPI, gRPC |
| Document Processing Agent (FR-165, FR-169) | 160 hrs | OCR, face matching, NID validation |
| Customer Service Chatbot (FR-164) | 120 hrs | Bengali NLP, 80% resolution rate |
| Fraud Detection ML Model (FR-166) | 140 hrs | Pattern recognition, anomaly detection |
| Predictive Analytics (FR-167) | 100 hrs | Risk assessment, premium optimization |
| Voice Assistant (FR-168, FG-015) | 180 hrs | Bengali STT/TTS, voice workflow |
| AI Training & Model Deployment | 80 hrs | ML pipeline, continuous learning |
| **SUBTOTAL** | **860 hrs** |  |
| **Buffer (10%)** | **86 hrs** |  |
| **TOTAL AI** | **946 hrs** |  |

Assignment: Python Dev 1 (50%) + Python Dev 2 (50%) = ~1 FTE for M3

________________________________________________________________________________

#### Remaining Portals (M3)

Portal 5: Customer Support Portal - 200 hrs

Support ticket queue

Call center integration

Customer history view

Resolution templates

Portal 6: DevOps Portal - 180 hrs

Grafana/Prometheus integration

System health monitoring

Alert management

Log aggregation

Portal 7-12: Additional Portals - 400 hrs

Database Manager Portal

Focal Person Portal

Partner Admin Portal

General Staff Portal

Vendor Portal

Marketing Page Admin

Total M3 Portals: 780 hrs

________________________________________________________________________________

#### Advanced Features (M3)

Performance Optimizations - 320 hrs

Database query optimization

Read replicas setup

Caching strategies (Redis)

CDN configuration

Advanced Security - 280 hrs

2FA enforcement (FR-017)

Enhanced fraud detection rules

Penetration testing

Security audit

Advanced Analytics - 240 hrs

Churn prediction (FR-150)

Customer lifetime value

Geographic risk heatmaps (FR-202)

Pre-built dashboards (FR-203)

________________________________________________________________________________

### M3 Effort Summary

| Component | Estimated Hours |
| --- | --- |
| IoT Integration & UBI | 757 hrs |
| AI Engine & Multi-Agent Network | 946 hrs |
| Remaining Portals (6) | 780 hrs |
| Performance Optimizations | 320 hrs |
| Advanced Security | 280 hrs |
| Advanced Analytics | 240 hrs |
| Voice Assistant Features | 180 hrs (in AI) |
| Additional Features | 400 hrs |
| QA & Testing | 640 hrs |
| Documentation & Training | 320 hrs |
| **TOTAL M3** | **4,863 hrs** |

M3 Available Capacity: 8,535 hours

M3 Status: ✅ Comfortable (3,672 hrs buffer for polish & optimization)

________________________________________________________________________________

## Summary: Final Project Capacity vs Effort (ALIGNED)

| Milestone | Available Hours | Required Hours | Utilization | Status |
| --- | --- | --- | --- | --- |
| **M1 (Beta - Mar 1)** | 4,040 hrs | 2,740 hrs | 68% | ✅ **COMFORTABLE** |
| **M2 (Launch - Apr 14)** | 2,256 hrs | 1,641 hrs | 73% | ✅ **COMFORTABLE** |
| **M3 (Complete - Aug 1)** | 6,768 hrs | 4,863 hrs | 72% | ✅ **COMFORTABLE** |
| **TOTAL** | **13,064 hrs** | **9,244 hrs** | **71%** | ✅ **ACHIEVABLE** |

Key Changes:

✅ M1: Customer Mobile App (Android + iOS) + 2 Portals with mocks (69% utilization)

✅ M2: Real API integration + Claims backend (73% utilization)

✅ M3: IoT + AI + 10 Portals + Advanced features (72% utilization)

✅ NO Agent Mobile App - Per SRS, agents use web portal on tablets

Team Allocation:

CTO 50%, Mamoon 40%, Sagor 50%, Python 50%, Sujon 60%, Rumon 60%, React 70%, QA 60%, Mobile/Backend 90%

________________________________________________________________________________

## Key Decisions & Trade-offs

### M1 Reductions (to meet capacity):

✅ Only 2 portals (Partner + System Admin) instead of 6 - Saves 378 hrs

✅ No Agent App in M1 - Saves 678 hrs

✅ Simplified Claims (manual approval only) - Saves 184 hrs

✅ Basic Mobile App (customer only, core features) - Saves 678 hrs

✅ Reduced DevOps (essential infra only) - Saves 145 hrs

### M2 Additions (Grand Launch):

✨ Business Admin Portal + Agent Portal

✨ Agent Mobile Apps (Android + iOS)

✨ Partner onboarding automation

✨ Commission engine

✨ Analytics & BI dashboards

### M3 Focus (as per SRS shift):

🚀 All IoT features (14 requirements) - 757 hrs

🤖 AI Engine & Multi-Agent Network - 946 hrs

🎯 Remaining 6 portals - 780 hrs

⚡ Performance & Security - 600 hrs

📊 Advanced Analytics - 240 hrs

________________________________________________________________________________

## Risk Mitigation for M1

106-hour deficit solutions:

✅ CTO 50% time = 240 hrs (sufficient to cover deficit)

✅ Mamoon 40% time + Sujon 100% can handle payment + ticketing

✅ Mobile devs can help with portal components (weeks 7-10)

✅ Simplified flows reduce complexity

✅ Existing code (1,420 hrs worth) reduces unknowns

Confidence Level: HIGH (with existing code reuse and team flexibility)

________________________________________________________________________________

________________________________________________________________________________

# Person-Wise Responsibility Matrix

## Overview

This document provides a detailed breakdown of responsibilities, tasks, and workload for each team member across all three milestones (M1, M2, M3).

________________________________________________________________________________

## Team Member Details & Availability

| # | Name | Role | Languages/Tech | Availability | Hours/Week | Total M1 Hours | Total M2 Hours | Total M3 Hours |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | **CTO** | Technical Lead | Go, Architecture | 50% coding | 24 hrs | 240 hrs | 115 hrs | 374 hrs |
| 2 | **Mamoon** | Senior Full Stack | Node.js, React | 40% | 19 hrs | 190 hrs | 92 hrs | 299 hrs |
| 3 | **Sujon Ahmed** | Full Stack Dev | Node.js, React | 60% (realistic) | 48 hrs | 288 hrs | 144 hrs | 432 hrs |
| 4 | **Rumon** | UI/UX Designer | Figma, Design | 60% (realistic) | 48 hrs | 288 hrs | 144 hrs | 432 hrs |
| 5 | **Nur Hossain** | Android Developer | Kotlin, Java | 90% (realistic) | 48 hrs | 432 hrs | 216 hrs | 648 hrs |
| 6 | **Sojol Ahmed** | iOS Developer | Swift | 90% (realistic) | 48 hrs | 432 hrs | 216 hrs | 648 hrs |
| 7 | **QA** | QA/Test Engineer | Testing | 60% (realistic) | 48 hrs | 288 hrs | 144 hrs | 432 hrs |
| 8 | **Sagor** | DevOps Engineer | Docker, K8s, Go | 50% | 24 hrs | 240 hrs | 115 hrs | 374 hrs |
| 9 | **React Dev** | Frontend Developer | React, Next.js | 70% (realistic) | 48 hrs | 336 hrs | 168 hrs | 504 hrs |
| 10 | **Project Manager** | PM | Agile, Scrum | 90% (realistic) | 48 hrs | 346 hrs | 216 hrs | 648 hrs |
| 11 | **Mr. Delowar** | C# Lead | C# .NET, gRPC | 90% (from Jan 15) | 48 hrs | 221 hrs | 230 hrs | 749 hrs |
| 12 | **C# Developer** | C# Developer | C# .NET, gRPC | 90% (realistic) | 48 hrs | 346 hrs | 216 hrs | 648 hrs |
| 13 | **Python Dev 1** | Python Developer | Python, FastAPI | 50% (M3 AI focus) | 24 hrs | 192 hrs | 115 hrs | 374 hrs |
| 14 | **Python Dev 2** | Python Developer | Python, FastAPI | 50% (M3 AI focus) | 24 hrs | 192 hrs | 115 hrs | 374 hrs |

Note on Utilization: This table shows AVAILABLE hours per week. Actual utilization varies by role:

CTO, Mamoon, Sagor, Python Devs: 40-50% (have other commitments)

Sujon, Rumon, QA, React Dev: 60-70% (realistic with meetings, blockers)

Mobile Devs, Backend Devs, PM: 90% (high utilization on focused work)

See 03_TeamCapacity.md for REALISTIC capacity calculations used in planning.

________________________________________________________________________________

## 1. CTO - Technical Lead & Gateway Developer

Availability: 50% coding time (50% management)

Primary Tech: Go, Architecture, API Gateway, Kafka, IoT Broker

Total Project Hours: 729 hours (240 M1 + 115 M2 + 374 M3)

### M1 Responsibilities (221 hours - Joins Jan 15, 2026)

| Service/Component | Hours | Description | Status |
| --- | --- | --- | --- |
| **API Gateway** | 40 hrs | Deploy and configure 50% existing code | 50% Ready |
| **Authentication Service** | 8 hrs | Deploy existing service, insurance customization | ✅ 100% Ready |
| **Authorization Service** | 8 hrs | Deploy existing service, role setup | ✅ 100% Ready |
| **DBManager Service** | 8 hrs | Deploy existing service, connection setup | ✅ 100% Ready |
| **Storage Manager Service** | 8 hrs | Deploy existing service, S3 integration | ✅ 100% Ready |
| **Notification Service (Kafka)** | 120 hrs | Kafka setup, email/SMS integration, templates | New Development |
| **IoT Broker Setup (20%)** | 16 hrs | Basic MQTT setup for future | 80% Ready |
| **Technical Leadership** | 24 hrs | Architecture reviews, code reviews, mentoring | Ongoing |
| **Integration Support** | 8 hrs | Service integration troubleshooting | As needed |
| **TOTAL M1** | **240 hrs** |  |  |

Primary Deliverables (M1):

✅ API Gateway deployed and functional

✅ All existing Go services deployed (Auth, Authz, DBManager, Storage)

🆕 Kafka-based Notification Service operational

📋 Technical architecture documentation

________________________________________________________________________________

### M2 Responsibilities (115 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **API Gateway Enhancements** | 30 hrs | Rate limiting, advanced routing, webhooks |
| **Notification Service v2** | 35 hrs | Advanced templates, multi-language, scheduling |
| **Integration Service Support** | 24 hrs | Support C# team with gRPC integration |
| **Technical Leadership** | 18 hrs | M2 architecture, performance optimization |
| **Production Support** | 8 hrs | M1 production issues, incident response |
| **TOTAL M2** | **115 hrs** |  |

________________________________________________________________________________

### M3 Responsibilities (374 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **IoT Broker Complete** | 120 hrs | Full MQTT setup, device management, 10K devices |
| **IoT Telemetry Processing** | 96 hrs | Kafka Streams, real-time & batch processing |
| **IoT Device Management Portal** | 80 hrs | Device registry, monitoring, health tracking |
| **API Gateway v3** | 24 hrs | Final optimizations, WebSocket support |
| **Technical Leadership** | 40 hrs | M3 architecture, IoT infrastructure |
| **Documentation** | 14 hrs | Technical docs, API documentation |
| **TOTAL M3** | **374 hrs** |  |

Primary Deliverables (M3):

🚀 Complete IoT infrastructure (10,000 devices supported)

📡 Real-time telemetry processing with Kafka

🔧 IoT device management system

📚 Complete technical documentation

________________________________________________________________________________

## 2. Mamoon - Senior Full Stack Developer

Availability: 40% (has other commitments)

Primary Tech: Node.js, React, MongoDB, Payment Integration

Total Project Hours: 613 hours

### M1 Responsibilities (190 hours)

| Service/Component | Hours | Description | Status |
| --- | --- | --- | --- |
| **Payment Service** | 120 hrs | Complete bKash integration (70% done), add Nagad | 70% Ready |
| **Ticketing Service** | 50 hrs | Basic ticket management, Node.js backend | New Development |
| **Payment Testing & Integration** | 12 hrs | End-to-end payment testing | Testing |
| **Code Reviews** | 8 hrs | Review Sujon's work | Ongoing |
| **TOTAL M1** | **190 hrs** |  |  |

Primary Deliverables (M1):

✅ bKash payment gateway 100% operational

🆕 Basic ticketing system for customer support

💳 Payment reconciliation and audit trail

________________________________________________________________________________

### M2 Responsibilities (92 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **Payment Service v2** | 36 hrs | Add Rocket, credit/debit cards, installment plans |
| **Ticketing Service v2** | 30 hrs | Advanced features, SLA tracking, escalation |
| **Commission Service Support** | 18 hrs | Support C# team with payment integrations |
| **Code Reviews** | 8 hrs | Node.js code reviews |
| **TOTAL M2** | **92 hrs** |  |

________________________________________________________________________________

### M3 Responsibilities (299 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **Payment Service v3** | 80 hrs | Blockchain integration, advanced reconciliation |
| **Ticketing Service v3** | 60 hrs | AI integration, auto-routing, chatbot integration |
| **Integration API Support** | 80 hrs | Partner payment integrations, webhooks |
| **Full-Stack Features** | 60 hrs | Various enhancements across platform |
| **Documentation** | 19 hrs | Payment integration guides, API docs |
| **TOTAL M3** | **299 hrs** |  |

________________________________________________________________________________

## 3. Sujon Ahmed - Mid-Level Full Stack Developer

Availability: 100% (exhaust)

Primary Tech: Node.js, React, PostgreSQL

Total Project Hours: 1,541 hours

### M1 Responsibilities (480 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **Ticketing Service (Backend)** | 100 hrs | Work with Mamoon on Node.js backend |
| **Partner Portal Support** | 80 hrs | Backend APIs for Partner Portal |
| **System Admin Portal Support** | 80 hrs | Backend APIs for System Admin Portal |
| **Database Schema Design** | 40 hrs | PostgreSQL schema for all services |
| **API Integration Layer** | 60 hrs | Connect frontend to backend services |
| **Testing & Bug Fixes** | 80 hrs | Backend testing, integration testing |
| **Code Reviews** | 20 hrs | Peer reviews |
| **Documentation** | 20 hrs | API documentation |
| **TOTAL M1** | **480 hrs** |  |

________________________________________________________________________________

### M2 Responsibilities (230 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **Business Admin Portal Backend** | 75 hrs | APIs for Business Admin Portal |
| **Agent Portal Backend** | 60 hrs | APIs for Agent Portal |
| **Analytics Backend Support** | 45 hrs | Data aggregation APIs |
| **Testing & Bug Fixes** | 38 hrs | M2 feature testing |
| **Documentation** | 12 hrs | API updates |
| **TOTAL M2** | **230 hrs** |  |

________________________________________________________________________________

### M3 Responsibilities (749 hours)

| Service/Component | Hours | Description |
| --- | --- | --- |
| **Remaining Portals Backend** | 200 hrs | APIs for 6 remaining portals |
| **Performance Optimization** | 120 hrs | Database query optimization, caching |
| **Advanced Features** | 200 hrs | Various backend enhancements |
| **Integration Support** | 100 hrs | EHR, third-party integrations |
| **Testing & Bug Fixes** | 100 hrs | M3 comprehensive testing |
| **Documentation** | 29 hrs | Complete backend documentation |
| **TOTAL M3** | **749 hrs** |  |

________________________________________________________________________________

________________________________________________________________________________